## Cover
LionDriver · DFM · AIAG-VDA 2019
DFMEA — device, integrated panda, harness, vehicle interfaces
Generated from assurance/08-analyses/fmea/analyses/dfmea.yaml. Do not edit: regenerate with tools/safety/fmea_review_xlsx.py.
Revision | 0.6 · draft
Baseline | BL-002
Rating tables | RT-2
Updated | 2026-10-16
Scope | Safety-relevant hardware of AC-001 at BL-002: comma 3X panda section (STM32H725, clock and watchdog, MCU supply, CAN transceivers), Toyota harness and relay box, SoC-MCU interface, siren path, enclosure and cooling. SoC, cameras and other QM hardware only where they couple into these (WP-A-03).
Team | Jherrod Thomas (Project maintainer, safety lead (reviewer/approver)); Claude (AI assistant) (Drafting assistance; ratings require human review)
Summary
Failure modes | 21
Rated causes | 30
AP High | 30
AP Medium | 0
AP Low | 0
Actions (open) | 15 (15)
FMEA-MSR (msr: complete) | 21 rated, 0 exempt; MSR AP H 21, M 0, L 0 (provisional table)
Monitoring M | 1–4: 0 · 5–6: 0 · 7–8: 6 · 9–10: 15 (see sheet MSR)
Legend
H | High: an action or a rationale is required
M | Medium: an action or a rationale is recommended
L | Low
Aa | Amber text: no test targets the cause (detection 9 or 10)
Yellow cells on the Worksheet: reviewer input (decision from the list, comment)
Review sign-off
Reviewer
Independence level
Date
Result (accepted / accepted with findings / rejected)
Findings reference

## Worksheet
FAILURE ANALYSIS (AIAG-VDA STEP 4) | [7 empty] | RISK ANALYSIS (STEP 5) |  |  |  |  | OPTIMIZATION (STEP 6) |  |  |  | REVIEW
Element | Function | Failure effects | Hazards | S | Failure mode | Cause | Failure cause | Prevention controls | O | Detection controls | D | AP | Actions | Status | Revised S/O/D | Revised AP | Reviewer decision | Reviewer comment
DFM-SE-002 Safety MCU STM32H725: core, flash, SRAM | DFM-FN-001 Execute the safety model and hold its code, constants and state without corruption | End Uncontrollable steering or unintended acceleration End Contributes to HZ-005 End Contributes to HZ-006 (deceleration limit or authority evaluated wrongly) Next higher Out-of-envelope or unauthorised command passes the panda Local Torque/acceleration limit or controls_allowed evaluated wrongly | HZ-002 HZ-005 HZ-006 | 10 | DFM-001 · degraded Safety check computes a wrong result (permanent CPU or data-path fault) | C1 | Permanent fault in the Cortex-M7 core or bus matrix; single core, no lockstep, no CPU self-test | • COTS comma 3X design in volume field use; no supplier reliability data, schematic or BOM available to LionDriver (WP-H-02 UK-01, UK-02) assurance/04-hardware/WP-H-02-hardware-design.md | 3 | • No LionDriver hardware verification or qualification test exists for this cause (WP-H-06/WP-H-07 not started; no HIL bench, D-04) | 10 | H | DFM-ACT-001 · prevention Add a CPU self-test (vendor STL if available for STM32H7) at start-up and periodically, or argue the ASIL B target without CPU coverage (WP-H-03 finding 4) | open
DFM-SE-002 Safety MCU STM32H725: core, flash, SRAM | DFM-FN-001 Execute the safety model and hold its code, constants and state without corruption | End Steering or acceleration beyond the envelope End Contributes to HZ-005 Next higher Panda enforces wrong limits Local Wrong limit value or wrong instruction | HZ-002 HZ-005 | 10 | DFM-002 · degraded Code or limit constants corrupted in flash during operation | C1 | Multi-bit flash error or cell degradation; double-error ECC flag not handled; image signature checked at boot only | • COTS comma 3X design in volume field use; no supplier reliability data, schematic or BOM available to LionDriver (WP-H-02 UK-01, UK-02) assurance/04-hardware/WP-H-02-hardware-design.md • Bootstub signature check at power-up (bootstub.c:47-72); flash ECC corrects single bits in silicon panda/board/bootstub.c | 2 | • No LionDriver hardware verification or qualification test exists for this cause (WP-H-06/WP-H-07 not started; no HIL bench, D-04) | 10 | H | DFM-ACT-002 · design change Integrate the G1 layer 1 MCU measures (RAMECC handling, redundant storage, code CRC, start-up RAM test, fault escalation) from panda branch liondriver/g1-layer1 after review and HIL evidence | open
DFM-SE-002 Safety MCU STM32H725: core, flash, SRAM | DFM-FN-001 Execute the safety model and hold its code, constants and state without corruption | End Unintended steering or acceleration End Contributes to HZ-002 End Contributes to HZ-005 End Contributes to HZ-006 (deceleration limit or authority corrupted) Next higher Unauthorised or out-of-envelope command passes Local Wrong authority or limit decision, or crash | HZ-001 HZ-002 HZ-005 HZ-006 | 10 | DFM-003 · degraded Safety state in SRAM corrupted (controls_allowed, limits, counters, stack) | C1 | Double-bit soft error or permanent SRAM fault; RAMECC monitors not configured, ECC interrupt not registered | • COTS comma 3X design in volume field use; no supplier reliability data, schematic or BOM available to LionDriver (WP-H-02 UK-01, UK-02) assurance/04-hardware/WP-H-02-hardware-design.md | 3 | • No LionDriver hardware verification or qualification test exists for this cause (WP-H-06/WP-H-07 not started; no HIL bench, D-04) | 10 | H | DFM-ACT-002 · design change Integrate the G1 layer 1 MCU measures (RAMECC handling, redundant storage, code CRC, start-up RAM test, fault escalation) from panda branch liondriver/g1-layer1 after review and HIL evidence | open
[6 empty] | C2 | Wrong-address write by the SPI DMA (no MPU) | • COTS comma 3X design in volume field use; no supplier reliability data, schematic or BOM available to LionDriver (WP-H-02 UK-01, UK-02) assurance/04-hardware/WP-H-02-hardware-design.md | 3 | • No LionDriver hardware verification or qualification test exists for this cause (WP-H-06/WP-H-07 not started; no HIL bench, D-04) | 10 | H | DFM-ACT-002 · design change Integrate the G1 layer 1 MCU measures (RAMECC handling, redundant storage, code CRC, start-up RAM test, fault escalation) from panda branch liondriver/g1-layer1 after review and HIL evidence | open
DFM-SE-003 MCU clock and independent watchdog (HSE, PLL, LSI, IWDG) | DFM-FN-002 Provide an accurate time base for all timeouts, and reset the MCU (releasing the relay) within 0.1 s if execution stops | End Stock AEB unavailable until power cycle Next higher Camera path stays cut; no stock PCS messages to the car Local Checks, TX and forwarding stop; relay holds last state | HZ-011 | 10 | DFM-004 · stuck MCU execution stops with the relay energised | C1 | Hang in an ISR or main loop, unused vector to Default_Handler, or assert_fatal loop | • IWDG (LSI), 90 ms nominal, window mode, started on every relay drive and fed only after safety-task and main-loop progress (BL-002, panda#1, #3); a reset floats the relay GPIO panda/board/drivers/hw_watchdog.h | 3 | • Watchdog HIL test with injected hangs (FAULT_INJECTION build); targeted, not yet run (no HIL bench, D-04) panda/tests/hitl/test_10_hw_watchdog.py | 8 | H | DFM-ACT-003 · detection Run the watchdog HIL test (test_10_hw_watchdog) on the bench and confirm the relay releases on reset (HWSR-502, UK-06) (D-04). The lead deferred the HIL bench (DQ-049, 2026-10-14), so this waits for the bench | open
DFM-SE-003 MCU clock and independent watchdog (HSE, PLL, LSI, IWDG) | DFM-FN-002 Provide an accurate time base for all timeouts, and reset the MCU (releasing the relay) within 0.1 s if execution stops | End Stale data used beyond the detection budget End Contributes to HZ-008 Next higher RX and heartbeat timeouts longer than specified; CAN errors Local All timeouts and the CAN bit timing shift | HZ-002 HZ-008 | 10 | DFM-005 · drift MCU time base wrong | C1 | HSE crystal drift or PLL misconfiguration; no cross-check against an independent oscillator | • COTS comma 3X design in volume field use; no supplier reliability data, schematic or BOM available to LionDriver (WP-H-02 UK-01, UK-02) assurance/04-hardware/WP-H-02-hardware-design.md • Clock security system on HSE loss (NMI, reset); register readback of RCC, report-only panda/board/stm32h7/clock.h | 3 | • No LionDriver hardware verification or qualification test exists for this cause (WP-H-06/WP-H-07 not started; no HIL bench, D-04) | 10 | H | DFM-ACT-004 · design change Cross-check the HSE-derived time base against LSI or HSI and react on deviation (HWSR-504a) | open
DFM-SE-003 MCU clock and independent watchdog (HSE, PLL, LSI, IWDG) | DFM-FN-002 Provide an accurate time base for all timeouts, and reset the MCU (releasing the relay) within 0.1 s if execution stops | End Stock AEB unavailable until power cycle Next higher A later hang leaves the relay energised Local Latent: the hang reaction is missing | HZ-011 | 10 | DFM-006 · loss Watchdog does not reset the MCU when execution stops | C1 | LSI oscillator failure or IWDG fault; reset path never proven in operation | • COTS comma 3X design in volume field use; no supplier reliability data, schematic or BOM available to LionDriver (WP-H-02 UK-01, UK-02) assurance/04-hardware/WP-H-02-hardware-design.md | 2 | • Watchdog HIL test proves the reset path on the bench; not yet run panda/tests/hitl/test_10_hw_watchdog.py | 8 | H | DFM-ACT-003 · detection Run the watchdog HIL test (test_10_hw_watchdog) on the bench and confirm the relay releases on reset (HWSR-502, UK-06) (D-04). The lead deferred the HIL bench (DQ-049, 2026-10-14), so this waits for the bench | open
DFM-SE-004 MCU power supply and supervision (board regulator, SMPS/LDO, BOR, PVD) | DFM-FN-003 Supply the MCU within its operating range, or hold it in reset | End Unintended steering or acceleration End Contributes to HZ-005 Next higher Wrong safety decisions while still running Local Undefined logic behaviour, flash read errors | HZ-002 HZ-005 | 10 | DFM-007 · insufficient MCU operates in the brown-out zone | C1 | Vehicle supply dip (cranking, alternator fault) with BOR level not set and PVD not enabled | • COTS comma 3X design in volume field use; no supplier reliability data, schematic or BOM available to LionDriver (WP-H-02 UK-01, UK-02) assurance/04-hardware/WP-H-02-hardware-design.md | 5 | • No LionDriver hardware verification or qualification test exists for this cause (WP-H-06/WP-H-07 not started; no HIL bench, D-04) | 10 | H | DFM-ACT-005 · design change Set the BOR level in the option bytes and enable PVD with a safe-state reaction (WP-H-02 DC-07); read the option bytes of a reference device (UK-04) | open
DFM-SE-005 CAN transceivers XCVR1-4 and enables | DFM-FN-004 Transmit and receive on buses 0, 1 and 2 without disturbing the vehicle bus | End Loss of assist and stock functions End Contributes to HZ-011 Next higher EPS, PCM and ADAS messages lost Local Vehicle CAN bus 0 blocked | HZ-004 HZ-011 | 10 | DFM-008 · stuck Car-side transceiver holds the bus dominant | C1 | XCVR1 TX driver fault or TXD stuck low | • COTS comma 3X design in volume field use; no supplier reliability data, schematic or BOM available to LionDriver (WP-H-02 UK-01, UK-02) assurance/04-hardware/WP-H-02-hardware-design.md | 3 | • No LionDriver hardware verification or qualification test exists for this cause (WP-H-06/WP-H-07 not started; no HIL bench, D-04) | 10 | H | DFM-ACT-006 · design change Disable a transceiver and enter the safe state on persistent error or bus-off (HWSR-508, WP-H-02 DC-04) | open
DFM-SE-005 CAN transceivers XCVR1-4 and enables | DFM-FN-004 Transmit and receive on buses 0, 1 and 2 without disturbing the vehicle bus | End Item disengages; loss of lateral control Next higher Panda RX checks time out; controls withdrawn Local No RX of vehicle messages | HZ-004 | 10 | DFM-009 · open Car-side transceiver receives nothing | C1 | XCVR1 RX open or stuck recessive | • COTS comma 3X design in volume field use; no supplier reliability data, schematic or BOM available to LionDriver (WP-H-02 UK-01, UK-02) assurance/04-hardware/WP-H-02-hardware-design.md | 3 | • Per-message RX timeout test (opendbc, CI) verifies the reaction in software, not the transceiver fault opendbc_repo/opendbc/safety/tests/test_toyota.py | 9 | H | DFM-ACT-006 · design change Disable a transceiver and enter the safe state on persistent error or bus-off (HWSR-508, WP-H-02 DC-04) | open
DFM-SE-006 Intercept switch (harness box U1/U2) and its drive | DFM-FN-005 Separate the camera from the car bus only while energised; restore the stock camera path whenever de-energised | End Stock AEB unavailable Next higher Stock PCS and LKA messages do not reach the car Local Camera disconnected from the car while the panda forwards nothing or is off | HZ-011 | 10 | DFM-010 · stuck Intercept switch stays in intercept when released | C1 | Analog switch U1 or U2 stuck in the intercept (NO) position, or its IN input damaged high | • COTS comma 3X design in volume field use; no supplier reliability data, schematic or BOM available to LionDriver (WP-H-02 UK-01, UK-02) assurance/04-hardware/WP-H-02-hardware-design.md | 3 | • No LionDriver hardware verification or qualification test exists for this cause (WP-H-06/WP-H-07 not started; no HIL bench, D-04) | 10 | H | DFM-ACT-007 · design change Add relay readback in a LionDriver harness adapter (WP-H-02 DC-03) and confirm the de-energised contact state (UK-03) | open
[6 empty] | C2 | SBU1 drive stuck high (device-side driver or MCU pin, UK-06) | • COTS comma 3X design in volume field use; no supplier reliability data, schematic or BOM available to LionDriver (WP-H-02 UK-01, UK-02) assurance/04-hardware/WP-H-02-hardware-design.md | 3 | • No LionDriver hardware verification or qualification test exists for this cause (WP-H-06/WP-H-07 not started; no HIL bench, D-04) | 10 | H | DFM-ACT-007 · design change Add relay readback in a LionDriver harness adapter (WP-H-02 DC-03) and confirm the de-energised contact state (UK-03) | open
[6 empty] | C3 | Pull-down R2 or R3 open, so IN floats when the device stops driving SBU1 (reset, watchdog, hang, unplugged cable) | • COTS comma 3X design in volume field use; no supplier reliability data, schematic or BOM available to LionDriver (WP-H-02 UK-01, UK-02) assurance/04-hardware/WP-H-02-hardware-design.md | 3 | • No LionDriver hardware verification or qualification test exists for this cause (WP-H-06/WP-H-07 not started; no HIL bench, D-04) | 10 | H | DFM-ACT-007 · design change Add relay readback in a LionDriver harness adapter (WP-H-02 DC-03) and confirm the de-energised contact state (UK-03) DFM-ACT-014 · detection Bench-test the harness box failure behaviour (RR-2026-010): box unpowered with car and camera powered; R2/R3 forced open with the device silent; supply at 14-16 V against the DG419LE ratings; pass-through signal integrity; clamp-diode short on CAN0; confirm the shipped box matches the v3 drawing (VS-HW-02) | open open
[6 empty] | C4 | U1/U2 overstressed or latched up by box supply transients above the DG419LE absolute maximum (V+ = VL = VIN with no regulator; the SMF16A clamp D4 only starts to conduct above its 16 V stand-off). Damage can leave the switch in either position or open a channel (also DFM-011, DFM-013) | • COTS comma 3X design in volume field use; no supplier reliability data, schematic or BOM available to LionDriver (WP-H-02 UK-01, UK-02) assurance/04-hardware/WP-H-02-hardware-design.md • D4 SMF16A TVS on VIN (harness box v3). Its clamp level against the DG419LE rating is not shown: datasheet limits not confirmed (RR-2026-010 F-05) assurance/04-hardware/reviews/RR-2026-010.md | 4 | • No LionDriver hardware verification or qualification test exists for this cause (WP-H-06/WP-H-07 not started; no HIL bench, D-04) | 10 | H | DFM-ACT-014 · detection Bench-test the harness box failure behaviour (RR-2026-010): box unpowered with car and camera powered; R2/R3 forced open with the device silent; supply at 14-16 V against the DG419LE ratings; pass-through signal integrity; clamp-diode short on CAN0; confirm the shipped box matches the v3 drawing (VS-HW-02) DFM-ACT-015 · detection Read the Vishay DG417LE/DG418LE/DG419LE datasheet (document 76432) and record the absolute maximum V+ to V-, VL and IN ratings, the single-supply operating range and VINH/VINL at VL = V+ = 14 V; compare with VIN including the D4 clamp level. If a limit is exceeded, raise it with comma.ai and with DQ-209 (RR-2026-010 F-05; blocked at 2026-10-16: vendor and datasheet hosts unreachable from the analysis environment) | open open
DFM-SE-006 Intercept switch (harness box U1/U2) and its drive | DFM-FN-005 Separate the camera from the car bus only while energised; restore the stock camera path whenever de-energised | End Erratic or excessive steering or braking End Contributes to HZ-006 Next higher Conflicting steering and ACC commands Local Stock camera LKA/ACC messages reach the car together with panda TX | HZ-002 HZ-006 | 10 | DFM-011 · stuck Intercept switch stays in pass-through when driven | C1 | Analog switch U1 or U2 stuck in the pass-through (NC) position, or SBU1 drive lost or held low (driver open, R2/R3 short) | • COTS comma 3X design in volume field use; no supplier reliability data, schematic or BOM available to LionDriver (WP-H-02 UK-01, UK-02) assurance/04-hardware/WP-H-02-hardware-design.md | 3 | • Relay-malfunction tests in the opendbc suite exercise the software reaction, not the relay opendbc_repo/opendbc/safety/tests/test_toyota.py | 9 | H | DFM-ACT-007 · design change Add relay readback in a LionDriver harness adapter (WP-H-02 DC-03) and confirm the de-energised contact state (UK-03) | open
[6 empty] | C2 | The 5 V SBU1 drive does not reach the DG419LE logic-high threshold with VL tied to VIN (about 14 V), so the switch does not change over or changes over only at some temperatures (RR-2026-010 F-05; thresholds at VL = VIN not confirmed) | • COTS comma 3X design in volume field use; no supplier reliability data, schematic or BOM available to LionDriver (WP-H-02 UK-01, UK-02) assurance/04-hardware/WP-H-02-hardware-design.md • Field use: openpilot on TSS2 Toyotas with this box would raise relayMalfunction on every drive if the switch never changed over, which suggests it switches at nominal conditions. Margin over temperature and supply is not shown assurance/04-hardware/reviews/RR-2026-010.md | 2 | • Relay-malfunction tests in the opendbc suite exercise the software reaction, not the switch threshold opendbc_repo/opendbc/safety/tests/test_toyota.py | 9 | H | DFM-ACT-014 · detection Bench-test the harness box failure behaviour (RR-2026-010): box unpowered with car and camera powered; R2/R3 forced open with the device silent; supply at 14-16 V against the DG419LE ratings; pass-through signal integrity; clamp-diode short on CAN0; confirm the shipped box matches the v3 drawing (VS-HW-02) DFM-ACT-015 · detection Read the Vishay DG417LE/DG418LE/DG419LE datasheet (document 76432) and record the absolute maximum V+ to V-, VL and IN ratings, the single-supply operating range and VINH/VINL at VL = V+ = 14 V; compare with VIN including the D4 clamp level. If a limit is exceeded, raise it with comma.ai and with DQ-209 (RR-2026-010 F-05; blocked at 2026-10-16: vendor and datasheet hosts unreachable from the analysis environment) | open open
DFM-SE-007 Harness, connectors, SBU orientation and ignition sense | DFM-FN-006 Connect the device to the vehicle buses, power and ignition, and report harness orientation correctly | End Loss of lateral control while engaged Next higher Item disengages; relay releases if the coil loses drive Local Panda loses CAN, power or relay drive | HZ-004 | 10 | DFM-012 · connection Harness disconnected or intermittent while driving | C1 | Connector not fully latched at installation, or vibration loosens it | • Owner installation per comma instructions; no LionDriver installation check yet (WP-O-01) assurance/09-production-operation/WP-O-01-installation-and-provisioning-control.md | 5 | • No LionDriver hardware verification or qualification test exists for this cause (WP-H-06/WP-H-07 not started; no HIL bench, D-04) | 10 | H | DFM-ACT-008 · detection Define the installation check, including a stock PCS/AEB function check and a harness latch check (WP-O-01, TSR-805) | open
DFM-SE-007 Harness, connectors, SBU orientation and ignition sense | DFM-FN-006 Connect the device to the vehicle buses, power and ignition, and report harness orientation correctly | End Stock AEB unavailable Next higher No stock PCS messages to the car Local Camera disconnected from the car | HZ-011 | 10 | DFM-013 · open Stock camera path open inside the harness box | C1 | Open in the harness box stock path (U1/U2 channel open, solder joint, connector contact) | • COTS comma 3X design in volume field use; no supplier reliability data, schematic or BOM available to LionDriver (WP-H-02 UK-01, UK-02) assurance/04-hardware/WP-H-02-hardware-design.md | 3 | • No LionDriver hardware verification or qualification test exists for this cause (WP-H-06/WP-H-07 not started; no HIL bench, D-04) | 10 | H | DFM-ACT-008 · detection Define the installation check, including a stock PCS/AEB function check and a harness latch check (WP-O-01, TSR-805) | open
DFM-SE-007 Harness, connectors, SBU orientation and ignition sense | DFM-FN-006 Connect the device to the vehicle buses, power and ignition, and report harness orientation correctly | End Longer actuation window after SoC loss Next higher Slower withdrawal after SoC loss; device stays powered Local Heartbeat timeout uses the 5 s ignition-on value | HZ-002 | 10 | DFM-014 · short Ignition sense reads on when the ignition is off | C1 | Ignition sense line shorted | • COTS comma 3X design in volume field use; no supplier reliability data, schematic or BOM available to LionDriver (WP-H-02 UK-01, UK-02) assurance/04-hardware/WP-H-02-hardware-design.md | 3 | • No LionDriver hardware verification or qualification test exists for this cause (WP-H-06/WP-H-07 not started; no HIL bench, D-04) | 10 | H | DFM-ACT-008 · detection Define the installation check, including a stock PCS/AEB function check and a harness latch check (WP-O-01, TSR-805) | open
[6 empty] | C2 | Ignition-sense transistor Q6 (DMN3200U, harness box) drain-source short, holding SBU2 low | • COTS comma 3X design in volume field use; no supplier reliability data, schematic or BOM available to LionDriver (WP-H-02 UK-01, UK-02) assurance/04-hardware/WP-H-02-hardware-design.md | 3 | • No LionDriver hardware verification or qualification test exists for this cause (WP-H-06/WP-H-07 not started; no HIL bench, D-04) | 10 | H | DFM-ACT-008 · detection Define the installation check, including a stock PCS/AEB function check and a harness latch check (WP-O-01, TSR-805) DFM-ACT-014 · detection Bench-test the harness box failure behaviour (RR-2026-010): box unpowered with car and camera powered; R2/R3 forced open with the device silent; supply at 14-16 V against the DG419LE ratings; pass-through signal integrity; clamp-diode short on CAN0; confirm the shipped box matches the v3 drawing (VS-HW-02) | open open
DFM-SE-008 SoC-MCU interface: SPI link, STM_RST_N, STM_BOOT0 | DFM-FN-007 Carry commands, CAN frames and heartbeat between SoC and MCU intact; keep the MCU running the signed application | End Wrong in-envelope actuation, or a wrong configuration request Next higher Wrong command executed; a TX frame still passes the envelope checks Local A command or CAN frame is changed in transit and passes the 8-bit XOR | HZ-002 | 10 | DFM-015 · emc Corrupted SoC-to-MCU transfer accepted | C1 | Bit errors on the SPI link (EMC, signal integrity); 8-bit XOR only, no sequence counter | • COTS comma 3X design in volume field use; no supplier reliability data, schematic or BOM available to LionDriver (WP-H-02 UK-01, UK-02) assurance/04-hardware/WP-H-02-hardware-design.md • 8-bit XOR on header and data, NACK on mismatch (drivers/spi.h:97-138); reference lock limits what a corrupted 0xdc can select (reference build only) panda/board/drivers/spi.h | 4 | • No LionDriver hardware verification or qualification test exists for this cause (WP-H-06/WP-H-07 not started; no HIL bench, D-04) | 10 | H | DFM-ACT-009 · design change Replace the 8-bit XOR with a CRC and add a sequence counter on the SoC-MCU link (GAP-10) | open
DFM-SE-008 SoC-MCU interface: SPI link, STM_RST_N, STM_BOOT0 | DFM-FN-007 Carry commands, CAN frames and heartbeat between SoC and MCU intact; keep the MCU running the signed application | End Any actuation hazard (unverified image), or loss of function End Contributes to HZ-005 Next higher Without a safety model, or with an unsigned image Local The MCU runs no or unverified safety firmware | HZ-002 HZ-005 | 10 | DFM-016 · connection MCU forced into the ROM bootloader or reflashed by the SoC | C1 | SoC drives STM_BOOT0/STM_RST_N (fault or compromise); no RDP/WRP; pandad recovery flashes a development bootstub | • COTS comma 3X design in volume field use; no supplier reliability data, schematic or BOM available to LionDriver (WP-H-02 UK-01, UK-02) assurance/04-hardware/WP-H-02-hardware-design.md | 4 | • No LionDriver hardware verification or qualification test exists for this cause (WP-H-06/WP-H-07 not started; no HIL bench, D-04) | 10 | H | DFM-ACT-010 · design change Implement D-09/D-10: LionDriver signing key, no debug key in release builds, WRP + RDP1, remove the development-bootstub recovery (LD-DES-001 DR-10..DR-16) | open
DFM-SE-009 SoC-independent acoustic warning path (siren) | DFM-FN-008 Sound a warning when the SoC is lost while engaged, independently of the SoC audio | End Loss of control without timely warning End Contributes to HZ-012 Next higher Driver not warned when control is withdrawn after SoC loss Local Siren silent | HZ-004 HZ-012 | 10 | DFM-017 · loss No SoC-independent warning on SoC loss | C1 | Siren shares the codec, amplifier or speaker with the SoC audio, which the faulty SoC powers down | • COTS comma 3X design in volume field use; no supplier reliability data, schematic or BOM available to LionDriver (WP-H-02 UK-01, UK-02) assurance/04-hardware/WP-H-02-hardware-design.md | 5 | • No LionDriver hardware verification or qualification test exists for this cause (WP-H-06/WP-H-07 not started; no HIL bench, D-04) | 10 | H | DFM-ACT-011 · detection Confirm the siren audio topology (UK-07) and add a start-up siren self-test (TSR-515/516) | open
[6 empty] | C2 | Siren path fault stays latent (no self-test) | • COTS comma 3X design in volume field use; no supplier reliability data, schematic or BOM available to LionDriver (WP-H-02 UK-01, UK-02) assurance/04-hardware/WP-H-02-hardware-design.md | 4 | • No LionDriver hardware verification or qualification test exists for this cause (WP-H-06/WP-H-07 not started; no HIL bench, D-04) | 10 | H | DFM-ACT-011 · detection Confirm the siren audio topology (UK-07) and add a start-up siren self-test (TSR-515/516) | open
DFM-SE-010 Enclosure, windscreen mount and cooling (fan, DTS) | DFM-FN-009 Keep the device mechanically secured and within its thermal operating range | End Unintended actuation or loss of control End Contributes to HZ-004 Next higher Unreliable safety checks or loss of function Local Timing and memory errors; possible resets | HZ-002 HZ-004 | 10 | DFM-018 · thermal MCU runs above its temperature rating | C1 | Sun-loaded windscreen enclosure plus SoC heat; fan stall; MCU temperature grade unknown (UK-02) | • COTS comma 3X design in volume field use; no supplier reliability data, schematic or BOM available to LionDriver (WP-H-02 UK-01, UK-02) assurance/04-hardware/WP-H-02-hardware-design.md • Host thermal policy and fan check (QM); MCU DTS read but no firmware reaction panda/board/stm32h7/lldts.h | 4 | • No LionDriver hardware verification or qualification test exists for this cause (WP-H-06/WP-H-07 not started; no HIL bench, D-04) | 10 | H | DFM-ACT-012 · design change React to MCU DTS out of range with the safe state (HWSR-509, DC-10); obtain the MCU temperature grade (UK-02) | open
DFM-SE-002 Safety MCU STM32H725: core, flash, SRAM | DFM-FN-004 Transmit and receive on buses 0, 1 and 2 without disturbing the vehicle bus | End Steering torque above the controllable bound End Contributes to HZ-005 (acceleration above the bound) End Contributes to HZ-006 (deceleration below the bound) Next higher Out-of-envelope steering or acceleration frame reaches the vehicle with a valid CAN CRC Local A frame that passed safety_tx_hook changes in the FDCAN message RAM, the FDCAN core or the transceiver | HZ-002 HZ-005 HZ-006 | 10 | DFM-019 · intermittent Approved CAN frame altered between the TX check and the bus | C1 | Soft error or permanent fault in the copy into FDCAN message RAM, the message RAM or the FDCAN core. The packet XOR is checked at the FDCAN load (fdcan.h:100) and covers only the software queue; the CAN CRC is computed after the fault | • COTS comma 3X design in volume field use; no supplier reliability data, schematic or BOM available to LionDriver (WP-H-02 UK-01, UK-02) assurance/04-hardware/WP-H-02-hardware-design.md • Packet XOR checked before the FDCAN load (software queue only) panda/board/drivers/fdcan.h | 3 | • No LionDriver hardware verification or qualification test exists for this cause (WP-H-06/WP-H-07 not started; no HIL bench, D-04) | 10 | H | DFM-ACT-013 · design change Implement TSR-517: read back the item's own TX frames from the bus and compare with the approved frame, revoking on a mismatch; enable RAMECC handling for the FDCAN message RAM if the H725 provides it | open
[6 empty] | C2 | Transceiver fault that changes bits on TX without a CAN error (not credible for a single bit, which the CAN CRC and the bit monitoring of the transmitting controller detect; kept until the transceiver part is known, WP-H-02 UK-01) | • COTS comma 3X design in volume field use; no supplier reliability data, schematic or BOM available to LionDriver (WP-H-02 UK-01, UK-02) assurance/04-hardware/WP-H-02-hardware-design.md | 2 | • No LionDriver hardware verification or qualification test exists for this cause (WP-H-06/WP-H-07 not started; no HIL bench, D-04) | 10 | H | DFM-ACT-013 · design change Implement TSR-517: read back the item's own TX frames from the bus and compare with the approved frame, revoking on a mismatch; enable RAMECC handling for the FDCAN message RAM if the H725 provides it | open
DFM-SE-006 Intercept switch (harness box U1/U2) and its drive | DFM-FN-005 Separate the camera from the car bus only while energised; restore the stock camera path whenever de-energised | End Stock AEB unavailable End Lateral assist lost without a LionDriver warning Next higher Stock camera cut off from the car and the car-side ADAS CAN disturbed; the device is also unpowered Local U1/U2 unpowered, so pass-through is not guaranteed; D2/D3 clamp CAN0 and CAN2 towards the dead VIN rail, which the device input loads (derived from the v3 drawing, to confirm on the bench) | HZ-011 HZ-004 | 10 | DFM-020 · loss Harness box loses its supply while the car is on | C1 | Ignition branch to the box open (crimp, connector) or D1 open, without comma power installed | • COTS comma 3X design in volume field use; no supplier reliability data, schematic or BOM available to LionDriver (WP-H-02 UK-01, UK-02) assurance/04-hardware/WP-H-02-hardware-design.md | 5 | • No LionDriver hardware verification or qualification test exists for this cause (WP-H-06/WP-H-07 not started; no HIL bench, D-04) | 10 | H | DFM-ACT-014 · detection Bench-test the harness box failure behaviour (RR-2026-010): box unpowered with car and camera powered; R2/R3 forced open with the device silent; supply at 14-16 V against the DG419LE ratings; pass-through signal integrity; clamp-diode short on CAN0; confirm the shipped box matches the v3 drawing (VS-HW-02) | open
[6 empty] | C2 | Box VIN shorted to ground (TVS D4 short, connector or wiring) | • COTS comma 3X design in volume field use; no supplier reliability data, schematic or BOM available to LionDriver (WP-H-02 UK-01, UK-02) assurance/04-hardware/WP-H-02-hardware-design.md | 3 | • No LionDriver hardware verification or qualification test exists for this cause (WP-H-06/WP-H-07 not started; no HIL bench, D-04) | 10 | H | DFM-ACT-014 · detection Bench-test the harness box failure behaviour (RR-2026-010): box unpowered with car and camera powered; R2/R3 forced open with the device silent; supply at 14-16 V against the DG419LE ratings; pass-through signal integrity; clamp-diode short on CAN0; confirm the shipped box matches the v3 drawing (VS-HW-02) | open
DFM-SE-006 Intercept switch (harness box U1/U2) and its drive | DFM-FN-005 Separate the camera from the car bus only while energised; restore the stock camera path whenever de-energised | End Stock AEB unavailable End Loss of lateral control with a late or no warning Next higher Car-side ADAS CAN or the camera bus cannot communicate; stock PCS messages lost Local D2 (car side, CAN0) or D3 (camera side, CAN2) shorts a CAN line to GND or VIN in either switch state | HZ-011 HZ-004 | 10 | DFM-021 · short Clamp diode short loads or grounds a vehicle bus in the harness box | C1 | Schottky clamp D2 or D3 (BAS40SDW) short or leaky | • COTS comma 3X design in volume field use; no supplier reliability data, schematic or BOM available to LionDriver (WP-H-02 UK-01, UK-02) assurance/04-hardware/WP-H-02-hardware-design.md | 3 | • No LionDriver hardware verification or qualification test exists for this cause (WP-H-06/WP-H-07 not started; no HIL bench, D-04) | 10 | H | DFM-ACT-014 · detection Bench-test the harness box failure behaviour (RR-2026-010): box unpowered with car and camera powered; R2/R3 forced open with the device silent; supply at 14-16 V against the DG419LE ratings; pass-through signal integrity; clamp-diode short on CAN0; confirm the shipped box matches the v3 drawing (VS-HW-02) | open

## Actions
Action | Kind | Description | Owner | Status | Causes | Revised S/O/D | Revised AP | Evidence
DFM-ACT-001 | prevention | Add a CPU self-test (vendor STL if available for STM32H7) at start-up and periodically, or argue the ASIL B target without CPU coverage (WP-H-03 finding 4) | Jherrod Thomas | open | DFM-001.C1
DFM-ACT-002 | design change | Integrate the G1 layer 1 MCU measures (RAMECC handling, redundant storage, code CRC, start-up RAM test, fault escalation) from panda branch liondriver/g1-layer1 after review and HIL evidence | Jherrod Thomas | open | DFM-002.C1 DFM-003.C1 DFM-003.C2
DFM-ACT-003 | detection | Run the watchdog HIL test (test_10_hw_watchdog) on the bench and confirm the relay releases on reset (HWSR-502, UK-06) (D-04). The lead deferred the HIL bench (DQ-049, 2026-10-14), so this waits for the bench | Jherrod Thomas | open | DFM-004.C1 DFM-006.C1
DFM-ACT-004 | design change | Cross-check the HSE-derived time base against LSI or HSI and react on deviation (HWSR-504a) | Jherrod Thomas | open | DFM-005.C1
DFM-ACT-005 | design change | Set the BOR level in the option bytes and enable PVD with a safe-state reaction (WP-H-02 DC-07); read the option bytes of a reference device (UK-04) | Jherrod Thomas | open | DFM-007.C1
DFM-ACT-006 | design change | Disable a transceiver and enter the safe state on persistent error or bus-off (HWSR-508, WP-H-02 DC-04) | Jherrod Thomas | open | DFM-008.C1 DFM-009.C1
DFM-ACT-007 | design change | Add relay readback in a LionDriver harness adapter (WP-H-02 DC-03) and confirm the de-energised contact state (UK-03) | Jherrod Thomas | open | DFM-010.C1 DFM-010.C2 DFM-010.C3 DFM-011.C1
DFM-ACT-008 | detection | Define the installation check, including a stock PCS/AEB function check and a harness latch check (WP-O-01, TSR-805) | Jherrod Thomas | open | DFM-012.C1 DFM-013.C1 DFM-014.C1 DFM-014.C2
DFM-ACT-009 | design change | Replace the 8-bit XOR with a CRC and add a sequence counter on the SoC-MCU link (GAP-10) | Jherrod Thomas | open | DFM-015.C1
DFM-ACT-010 | design change | Implement D-09/D-10: LionDriver signing key, no debug key in release builds, WRP + RDP1, remove the development-bootstub recovery (LD-DES-001 DR-10..DR-16) | Jherrod Thomas | open | DFM-016.C1
DFM-ACT-011 | detection | Confirm the siren audio topology (UK-07) and add a start-up siren self-test (TSR-515/516) | Jherrod Thomas | open | DFM-017.C1 DFM-017.C2
DFM-ACT-012 | design change | React to MCU DTS out of range with the safe state (HWSR-509, DC-10); obtain the MCU temperature grade (UK-02) | Jherrod Thomas | open | DFM-018.C1
DFM-ACT-013 | design change | Implement TSR-517: read back the item's own TX frames from the bus and compare with the approved frame, revoking on a mismatch; enable RAMECC handling for the FDCAN message RAM if the H725 provides it | Jherrod Thomas | open | DFM-019.C1 DFM-019.C2
DFM-ACT-014 | detection | Bench-test the harness box failure behaviour (RR-2026-010): box unpowered with car and camera powered; R2/R3 forced open with the device silent; supply at 14-16 V against the DG419LE ratings; pass-through signal integrity; clamp-diode short on CAN0; confirm the shipped box matches the v3 drawing (VS-HW-02) | Jherrod Thomas | open | DFM-010.C3 DFM-010.C4 DFM-011.C2 DFM-014.C2 DFM-020.C1 DFM-020.C2 DFM-021.C1
DFM-ACT-015 | detection | Read the Vishay DG417LE/DG418LE/DG419LE datasheet (document 76432) and record the absolute maximum V+ to V-, VL and IN ratings, the single-supply operating range and VINH/VINL at VL = V+ = 14 V; compare with VIN including the D4 clamp level. If a limit is exceeded, raise it with comma.ai and with DQ-209 (RR-2026-010 F-05; blocked at 2026-10-16: vendor and datasheet hosts unreachable from the analysis environment) | Jherrod Thomas | open | DFM-010.C4 DFM-011.C2

## Structure
Element | Name | Kind | Parent | Functions
DFM-SE-001 | Item hardware: comma 3X with integrated panda, Toyota harness and relay box, installed in a Corolla E210 · ZRE212 · US (CFG-001) | system
DFM-SE-002 | Safety MCU STM32H725: core, flash, SRAM | subsystem | DFM-SE-001 | DFM-FN-001: Execute the safety model and hold its code, constants and state without corruption
DFM-SE-003 | MCU clock and independent watchdog (HSE, PLL, LSI, IWDG) | component | DFM-SE-002 | DFM-FN-002: Provide an accurate time base for all timeouts, and reset the MCU (releasing the relay) within 0.1 s if execution stops
DFM-SE-004 | MCU power supply and supervision (board regulator, SMPS/LDO, BOR, PVD) | component | DFM-SE-001 | DFM-FN-003: Supply the MCU within its operating range, or hold it in reset
DFM-SE-005 | CAN transceivers XCVR1-4 and enables | component | DFM-SE-001 | DFM-FN-004: Transmit and receive on buses 0, 1 and 2 without disturbing the vehicle bus
DFM-SE-006 | Intercept switch (harness box U1/U2) and its drive | component | DFM-SE-001 | DFM-FN-005: Separate the camera from the car bus only while energised; restore the stock camera path whenever de-energised
DFM-SE-007 | Harness, connectors, SBU orientation and ignition sense | interface | DFM-SE-001 | DFM-FN-006: Connect the device to the vehicle buses, power and ignition, and report harness orientation correctly
DFM-SE-008 | SoC-MCU interface: SPI link, STM_RST_N, STM_BOOT0 | interface | DFM-SE-001 | DFM-FN-007: Carry commands, CAN frames and heartbeat between SoC and MCU intact; keep the MCU running the signed application
DFM-SE-009 | SoC-independent acoustic warning path (siren) | component | DFM-SE-001 | DFM-FN-008: Sound a warning when the SoC is lost while engaged, independently of the SoC audio
DFM-SE-010 | Enclosure, windscreen mount and cooling (fan, DTS) | component | DFM-SE-001 | DFM-FN-009: Keep the device mechanically secured and within its thermal operating range

## MSR
FMEA-MSR (monitoring and system response, msr-plan.md): S, F, M and MSR AP per rating-tables.md §7 (RT-2). The MSR AP table is provisional until the handbook table is transcribed (decision register DQ-207). Exempt causes are rated in the FMEA named in the reason.
Failure mode | S | Cause | Failure cause | Diagnostic | System response | Effect after the response | S after | F | M | MSR AP | Timing (FTTI · FDTI + FRTI) | Basis | Monitoring actions | Reviewer decision | Reviewer comment
DFM-001 · Safety check computes a wrong result (permanent CPU or data-path fault) | 10 | DFM-001.C1 | Permanent fault in the Cortex-M7 core or bus matrix; single core, no lockstep, no CPU self-test | None in the MCU at BL-002. The host compares controls_allowed after about 2 s (QM); it does not check limits | None for a wrong limit result | Unchanged: a wrong check result lets an over-limit or unauthorised frame through | 10 | 6 | 9 | H |  | unknown | DFM-ACT-001 · open
DFM-002 · Code or limit constants corrupted in flash during operation | 10 | DFM-002.C1 | Multi-bit flash error or cell degradation; double-error ECC flag not handled; image signature checked at boot only | Bootstub signature check at power-up only; no periodic code CRC in the pinned firmware | None during the drive | Unchanged until the next power-up | 10 | 4 | 9 | H |  | unknown | DFM-ACT-002 · open
DFM-003 · Safety state in SRAM corrupted (controls_allowed, limits, counters, stack) | 10 | DFM-003.C1 | Double-bit soft error or permanent SRAM fault; RAMECC monitors not configured, ECC interrupt not registered | None at BL-002: RAMECC monitors not configured, no redundant storage | None | Unchanged | 10 | 5 | 10 | H |  | unknown | DFM-ACT-002 · open
DFM-003 · Safety state in SRAM corrupted (controls_allowed, limits, counters, stack) | 10 | DFM-003.C2 | Wrong-address write by the SPI DMA (no MPU) | None at BL-002: no MPU and no redundant storage of the safety state | None | Unchanged | 10 | 3 | 10 | H |  | unknown | DFM-ACT-002 · open
DFM-004 · MCU execution stops with the relay energised | 10 | DFM-004.C1 | Hang in an ISR or main loop, unused vector to Default_Handler, or assert_fatal loop | IWDG expires about 90 ms after the last feed (T-09a). Timing fits on paper, but whether the reset releases the relay is unconfirmed (HWSR-502, UK-06) and the LSI tolerance leaves no shown margin (OI-7), so the response is not credited | MCU reset; relay de-energised if the drive circuit is de-energise-to-safe; stock camera CAN restored | Stock PCS/AEB restored and assist lost, if the relay releases | 10 | 6 | 7 | H | SG-07 forwarding loss · 200 ms 90 + 100 ms | code derived | DFM-ACT-003 · open
DFM-007 · MCU operates in the brown-out zone | 10 | DFM-007.C1 | Vehicle supply dip (cranking, alternator fault) with BOR level not set and PVD not enabled | None at BL-002: PVD handler is a stub and the BOR level is unknown (UK-04) | None | Unchanged: erratic MCU behaviour in the brown-out zone | 10 | 5 | 10 | H |  | unknown | DFM-ACT-005 · open
DFM-008 · Car-side transceiver holds the bus dominant | 10 | DFM-008.C1 | XCVR1 TX driver fault or TXD stuck low | FDCAN error counters; core reset on bus-off. The transceiver dominant timeout is part dependent and unknown | A core reset does not release a transceiver that holds the bus dominant; no safe-state reaction | Car bus blocked: loss of assist and of stock CAN functions until the transceiver times out, if it does | 10 | 5 | 8 | H |  | unknown | DFM-ACT-006 · open
DFM-009 · Car-side transceiver receives nothing | 10 | DFM-009.C1 | XCVR1 RX open or stuck recessive | RX timeout after 5 periods (about 0.16 s) withdraws controls_allowed; the host warns through the 2 s controlsMismatch counter (T-17) | Authority withdrawn at once; warning about 2.2 s after onset, beyond the 1 s budget to warning | Assist lost; warning late | 10 | 5 | 8 | H | SG-02/06 loss without warning · 1000 ms 160 + 2000 ms | code derived | DFM-ACT-006 · open
DFM-010 · Intercept switch stays in intercept when released | 10 | DFM-010.C1 | Analog switch U1 or U2 stuck in the intercept (NO) position, or its IN input damaged high | None: no relay readback (GAP-12) | None | Unchanged: stock camera stays cut off after release is commanded | 10 | 6 | 10 | H |  | unknown | DFM-ACT-007 · open
DFM-010 · Intercept switch stays in intercept when released | 10 | DFM-010.C2 | SBU1 drive stuck high (device-side driver or MCU pin, UK-06) | None: no relay readback (GAP-12) | None | Unchanged: stock camera stays cut off after release is commanded | 10 | 4 | 10 | H |  | unknown | DFM-ACT-007 · open
DFM-010 · Intercept switch stays in intercept when released | 10 | DFM-010.C3 | Pull-down R2 or R3 open, so IN floats when the device stops driving SBU1 (reset, watchdog, hang, unplugged cable) | None: the open pull-down is latent while the device drives SBU1, and no readback exists (GAP-12) | None | Unchanged: the switch may stay in intercept with the device silent, so the stock camera stays cut off | 10 | 2 | 10 | H |  | unknown | DFM-ACT-007 · open DFM-ACT-014 · open
DFM-010 · Intercept switch stays in intercept when released | 10 | DFM-010.C4 | U1/U2 overstressed or latched up by box supply transients above the DG419LE absolute maximum (V+ = VL = VIN with no regulator; the SMF16A clamp D4 only starts to conduct above its 16 V stand-off). Damage can leave the switch in either position or open a channel (also DFM-011, DFM-013) | None: no relay readback (GAP-12) and no supervision of the box supply | None | Unchanged: the stock camera may stay cut off after release is commanded | 10 | 4 | 10 | H |  | unknown | DFM-ACT-014 · open DFM-ACT-015 · open
DFM-011 · Intercept switch stays in pass-through when driven | 10 | DFM-011.C1 | Analog switch U1 or U2 stuck in the pass-through (NC) position, or SBU1 drive lost or held low (driver open, R2/R3 short) | Relay malfunction: a stock camera frame on the car side after the 1 s grace blocks all TX (T-08, 1-2 s) | All TX blocked; host raises relayMalfunction (IMMEDIATE_DISABLE) | Up to 2 s of stock LKA and item commands on the bus together, then no item output | 10 | 6 | 8 | H | SG-01 relay stuck · 500 ms 2000 + 10 ms | code derived | DFM-ACT-007 · open
DFM-011 · Intercept switch stays in pass-through when driven | 10 | DFM-011.C2 | The 5 V SBU1 drive does not reach the DG419LE logic-high threshold with VL tied to VIN (about 14 V), so the switch does not change over or changes over only at some temperatures (RR-2026-010 F-05; thresholds at VL = VIN not confirmed) | Relay malfunction: a stock camera frame on the car side after the 1 s grace blocks all TX (T-08, 1-2 s) | All TX blocked; host raises relayMalfunction (IMMEDIATE_DISABLE) | Up to 2 s of stock LKA and item commands on the bus together, then no item output | 10 | 2 | 8 | H | SG-01 relay stuck · 500 ms 2000 + 10 ms | code derived | DFM-ACT-014 · open DFM-ACT-015 · open
DFM-012 · Harness disconnected or intermittent while driving | 10 | DFM-012.C1 | Connector not fully latched at installation, or vibration loosens it | RX timeouts and host canBusMissing cover a partial disconnect only; a full disconnect also removes the device supply, so nothing warns | Relay drops out with the supply; stock camera restored | Assist lost without a LionDriver warning | 10 | 5 | 9 | H |  | unknown | DFM-ACT-008 · open
DFM-016 · MCU forced into the ROM bootloader or reflashed by the SoC | 10 | DFM-016.C1 | SoC drives STM_BOOT0/STM_RST_N (fault or compromise); no RDP/WRP; pandad recovery flashes a development bootstub | Bootstub signature check exists but accepts the debug key in debug builds; RDP and WRP not set (GAP-24) | None for a signed debug image | Unchanged | 10 | 4 | 9 | H |  | unknown | DFM-ACT-010 · open
DFM-019 · Approved CAN frame altered between the TX check and the bus | 10 | DFM-019.C1 | Soft error or permanent fault in the copy into FDCAN message RAM, the message RAM or the FDCAN core. The packet XOR is checked at the FDCAN load (fdcan.h:100) and covers only the software queue; the CAN CRC is computed after the fault | None after the FDCAN load: no TX read-back (TSR-517 not implemented) | None | Unchanged | 10 | 4 | 10 | H |  | unknown | DFM-ACT-013 · open
DFM-019 · Approved CAN frame altered between the TX check and the bus | 10 | DFM-019.C2 | Transceiver fault that changes bits on TX without a CAN error (not credible for a single bit, which the CAN CRC and the bit monitoring of the transmitting controller detect; kept until the transceiver part is known, WP-H-02 UK-01) | None: no TX read-back (TSR-517 not implemented) | None | Unchanged | 10 | 2 | 10 | H |  | unknown | DFM-ACT-013 · open
DFM-020 · Harness box loses its supply while the car is on | 10 | DFM-020.C1 | Ignition branch to the box open (crimp, connector) or D1 open, without comma power installed | None: the box supply is not supervised, and the device loses power with it | None | Unchanged | 10 | 5 | 10 | H |  | unknown | DFM-ACT-014 · open
DFM-020 · Harness box loses its supply while the car is on | 10 | DFM-020.C2 | Box VIN shorted to ground (TVS D4 short, connector or wiring) | None: the box supply is not supervised, and the device loses power with it | None | Unchanged | 10 | 3 | 10 | H |  | unknown | DFM-ACT-014 · open
DFM-021 · Clamp diode short loads or grounds a vehicle bus in the harness box | 10 | DFM-021.C1 | Schottky clamp D2 or D3 (BAS40SDW) short or leaky | RX timeouts withdraw control and the host raises CAN errors; nothing restores the bus | Authority withdrawn and the driver warned; the stock camera path stays broken | Item disengaged, but stock AEB stays unavailable | 10 | 3 | 8 | H |  | unknown | DFM-ACT-014 · open