## 00_Title_Page
Safety Plan
ISO 26262-2, Section 6
| Project | LionDriver Level 2 Driver Assistance Platform
| Document ID | LD-SPL-001
| Revision | 0.1 (draft)
| Date | 2026-10-09
| Functional Safety Manager | Jherrod Thomas
| FSM Email | via GitHub: @jherrodthomas
| Company | LionDriver open-source project
| Target ASIL | D
| Vehicle Programs | Platform analyzed as a Safety Element out of Context (ISO 26262-10 §9). First configuration: 2020 Toyota Corolla LE (U.S.), opendbc platform TOYOTA_COROLLA_TSS2. Target ASIL D is a provisional planning assumption pending the HARA.
| Key Suppliers | Upstream software: comma.ai openpilot, panda, opendbc (no supplier agreement; changes tracked by commit pin). Hardware: comma device and harness (commercial off-the-shelf, no development interface agreement).

## 01_Document_Control
Document Control
Revision | Date | Author | Description of Change | Approver
0.1 |  |  | Initial draft
0.2 |  |  | Internal review
1.0 |  |  | Released

## 02_Project_Info
Project Information
Project Name | LionDriver Level 2 Driver Assistance Platform
Document ID | LD-SPL-001
Item Name / Abbreviation
Target ASIL | D
Vehicle Programs | Platform analyzed as a Safety Element out of Context (ISO 26262-10 §9). First configuration: 2020 Toyota Corolla LE (U.S.), opendbc platform TOYOTA_COROLLA_TSS2. Target ASIL D is a provisional planning assumption pending the HARA.
Key Suppliers | Upstream software: comma.ai openpilot, panda, opendbc (no supplier agreement; changes tracked by commit pin). Hardware: comma device and harness (commercial off-the-shelf, no development interface agreement).
Project Start Date
Planned Release Date
Planned FSC Review Date

## 03_Roles_Responsibilities
Roles and Responsibilities
Name | Role | Organization | Email | Independence Level
Jherrod Thomas | Functional Safety Manager | LionDriver | @jherrodthomas | Overall responsible party
Jherrod Thomas (interim) | Project Manager | LionDriver | @jherrodthomas | N/A
VACANT | Safety-layer Software Lead (panda / opendbc safety modes) | LionDriver contributors |  | N/A (author role)
VACANT | Hardware Lead (panda, harness) | LionDriver contributors |  | N/A (author role)
VACANT | SOTIF and AI Safety Lead (ISO 21448, ISO/PAS 8800) | LionDriver contributors |  | N/A (author role)
VACANT | Cybersecurity Manager (ISO/SAE 21434) | LionDriver contributors |  | N/A
VACANT | Confirmation Reviewer | Must be outside the authoring team |  | I3 required for ASIL D work products (ISO 26262-2 Table 1)
VACANT | Functional Safety Assessor | External organization |  | I3
N/A | Upstream interface (comma.ai) | comma.ai |  | No formal relationship: upstream changes enter only through the change workflow and impact analysis

## 04_Tailoring
Tailoring of ISO 26262 Activities
ISO 26262 Clause / Part | Applicable (Yes/No/Partial) | Justification
Part 1 (Vocabulary) | Yes | Terminology used throughout.
Part 2 (Management of functional safety) | Yes | Safety plan, safety culture, confirmation measures and safety case. Independence requirements cannot currently be met (single maintainer); confirmation reviews are blocked until independent reviewers are recruited.
Part 3 (Concept phase) | Yes | Item definition, HARA, safety goals and functional safety concept, at platform level (SEooC) with assumptions verified per vehicle configuration.
Part 4 (Product development: system level) | Yes | Technical safety concept, item integration and testing, safety validation.
Part 5 (Product development: hardware level) | Partial | Applies to the panda and harness only. Vehicle ECUs are outside the item. The comma device application processor is QM; safety relies on the panda checker.
Part 6 (Product development: software level) | Yes | Full rigor for the panda firmware and brand safety modes. openpilot driving software is argued as QM behind the checker, subject to the independence argument in the TSC.
Part 7 (Production, operation, service, decommissioning) | No | Research platform; no production. Revisit before any hardware distribution or field deployment.
Part 8 (Supporting processes) | Yes | Configuration and change management, verification, documentation, tool qualification (Clause 11), qualification of existing software (Clause 12). Clause 5 distributed development: no DIA possible with upstream; treated as qualification of existing software.
Part 9 (ASIL-oriented and safety-oriented analyses) | Yes | Possible ASIL decomposition between the openpilot stack and the panda checker; dependent-failure analysis to support it.
Part 10 (Guidelines) | Yes | Safety Element out of Context approach (Clause 9) for the platform.
Part 11 (Semiconductors) | Partial | Consulted for the panda microcontroller's safety mechanisms and failure modes.
Part 12 (Motorcycles) | No | Passenger cars and light SUVs only.

## 05_Work_Products
Work Products
WP_ID | Work Product Name | ISO 26262 Reference | Owner | Target ASIL | Planned Date | Actual Date | Status
WP-MGT-01 | Safety plan | 26262-2 §6 | Jherrod Thomas | D | 2026-Q4 |  | In Progress
WP-MGT-02 | Cybersecurity plan | 21434 §6 | Cybersecurity Manager (vacant) | N/A (CAL) | 2027-Q1 |  | Not Started
WP-MGT-03 | Standards application and tailoring | 26262-2 §6 | Jherrod Thomas | D | 2026-Q4 |  | In Progress
WP-MGT-04 | Confirmation measures plan and records | 26262-2 §6 | Jherrod Thomas | D | 2027-Q1 |  | Not Started
WP-CON-01 | Item definition and operating envelope | 26262-3 §5 · 21448 §5 | Jherrod Thomas | D | 2026-Q4 |  | Draft complete
WP-CON-02 | HARA and safety goals | 26262-3 §6 | Jherrod Thomas | D | 2026-Q4 |  | Draft complete
WP-CON-03 | Assumptions register (SEooC) | 26262-10 §9 | Jherrod Thomas | D | 2026-Q4 |  | In Progress
WP-CON-04 | SOTIF hazard identification and triggering conditions | 21448 §6–7 | SOTIF and AI Safety Lead (vacant) | N/A (SOTIF) | 2027-Q1 |  | Not Started
WP-CON-05 | TARA and cybersecurity goals | 21434 §15, §9 | Cybersecurity Manager (vacant) | N/A (CAL) | 2027-Q1 |  | Not Started
WP-CON-06 | AI safety requirements for learned components | ISO/PAS 8800 | SOTIF and AI Safety Lead (vacant) | QM + SOTIF | 2027-Q2 |  | Not Started
WP-CON-07 | Functional safety concept | 26262-3 §7 | Jherrod Thomas | D | 2027-Q1 |  | Draft complete
WP-SYS-01 | Technical safety concept | 26262-4 §6 | Jherrod Thomas | D | 2027-Q2 |  | Not Started
WP-SYS-02 | Assessment of existing openpilot software and hardware | 26262-8 §12 | Safety-layer Software Lead (vacant) | D | 2027-Q2 |  | Not Started
WP-SW-01 | Software safety requirements (panda safety layer) | 26262-6 §6 | Safety-layer Software Lead (vacant) | D | 2027-Q2 |  | Not Started
WP-SW-02 | Unit verification of the safety layer | 26262-6 §9 | Safety-layer Software Lead (vacant) | D | 2027-Q3 |  | In Progress
WP-HW-01 | Hardware safety requirements and metrics (panda, harness) | 26262-5 §6, §8–9 | Hardware Lead (vacant) | D | 2027-Q3 |  | Not Started
WP-VV-01 | Integration and HIL test specification | 26262-4 §7 · 26262-6 §10 | Safety-layer Software Lead (vacant) | D | 2027-Q3 |  | Not Started
WP-VV-02 | Scenario catalog and SOTIF validation | 21448 §9–11 | SOTIF and AI Safety Lead (vacant) | N/A (SOTIF) | 2027-Q4 |  | Not Started
WP-VV-03 | Safety validation report (per configuration) | 26262-4 §8 | Jherrod Thomas | D | 2027-Q4 |  | Not Started
WP-ASR-01 | Safety case | 26262-2 §6 · UL 4600 | Jherrod Thomas | D | 2028-Q1 |  | Not Started
WP-ASR-02 | Tool qualification records | 26262-8 §11 | Jherrod Thomas | D | 2027-Q2 |  | Not Started

## 06_Confirmation_Reviews
Confirmation Reviews
WP_ID | Work Product | Required Independence (per ASIL) | Assigned Reviewer | Planned Date | Actual Date | Status | Notes
WP-MGT-01 | Safety plan | I3 |  |  |  | Not Started | Blocked until an independent reviewer is assigned (anomaly A01).
WP-MGT-02 | Cybersecurity plan | I1 |  |  |  | Not Started | Blocked until an independent reviewer is assigned (anomaly A01). No ASIL: independence shown is the minimum this plan sets for non-ASIL work products.
WP-MGT-03 | Standards application and tailoring | I3 |  |  |  | Not Started | Blocked until an independent reviewer is assigned (anomaly A01).
WP-MGT-04 | Confirmation measures plan and records | I3 |  |  |  | Not Started | Blocked until an independent reviewer is assigned (anomaly A01).
WP-CON-01 | Item definition and operating envelope | I3 |  |  |  | Not Started | Blocked until an independent reviewer is assigned (anomaly A01).
WP-CON-02 | HARA and safety goals | I3 |  |  |  | Not Started | Blocked until an independent reviewer is assigned (anomaly A01).
WP-CON-03 | Assumptions register (SEooC) | I3 |  |  |  | Not Started | Blocked until an independent reviewer is assigned (anomaly A01).
WP-CON-04 | SOTIF hazard identification and triggering conditions | I1 |  |  |  | Not Started | Blocked until an independent reviewer is assigned (anomaly A01). No ASIL: independence shown is the minimum this plan sets for non-ASIL work products.
WP-CON-05 | TARA and cybersecurity goals | I1 |  |  |  | Not Started | Blocked until an independent reviewer is assigned (anomaly A01). No ASIL: independence shown is the minimum this plan sets for non-ASIL work products.
WP-CON-06 | AI safety requirements for learned components | I1 |  |  |  | Not Started | Blocked until an independent reviewer is assigned (anomaly A01). No ASIL: independence shown is the minimum this plan sets for non-ASIL work products.
WP-CON-07 | Functional safety concept | I3 |  |  |  | Not Started | Blocked until an independent reviewer is assigned (anomaly A01).
WP-SYS-01 | Technical safety concept | I3 |  |  |  | Not Started | Blocked until an independent reviewer is assigned (anomaly A01).
WP-SYS-02 | Assessment of existing openpilot software and hardware | I3 |  |  |  | Not Started | Blocked until an independent reviewer is assigned (anomaly A01).
WP-SW-01 | Software safety requirements (panda safety layer) | I3 |  |  |  | Not Started | Blocked until an independent reviewer is assigned (anomaly A01).
WP-SW-02 | Unit verification of the safety layer | I3 |  |  |  | Not Started | Blocked until an independent reviewer is assigned (anomaly A01).
WP-HW-01 | Hardware safety requirements and metrics (panda, harness) | I3 |  |  |  | Not Started | Blocked until an independent reviewer is assigned (anomaly A01).
WP-VV-01 | Integration and HIL test specification | I3 |  |  |  | Not Started | Blocked until an independent reviewer is assigned (anomaly A01).
WP-VV-02 | Scenario catalog and SOTIF validation | I1 |  |  |  | Not Started | Blocked until an independent reviewer is assigned (anomaly A01). No ASIL: independence shown is the minimum this plan sets for non-ASIL work products.
WP-VV-03 | Safety validation report (per configuration) | I3 |  |  |  | Not Started | Blocked until an independent reviewer is assigned (anomaly A01).
WP-ASR-01 | Safety case | I3 |  |  |  | Not Started | Blocked until an independent reviewer is assigned (anomaly A01).
WP-ASR-02 | Tool qualification records | I3 |  |  |  | Not Started | Blocked until an independent reviewer is assigned (anomaly A01).

## 07_Tools
Tools
Tool Name | Vendor | Version | Usage in Safety Lifecycle | TCL | TCL Rationale | Qualification Status
arm-none-eabi-gcc | Arm GNU Toolchain | As pinned by the panda build | Compiles the panda safety-layer firmware | TCL3 (provisional) | TI2: a compiler error can introduce a fault in safety firmware. TD3 until a detection argument exists. Planned route to TCL2: back-to-back testing of the compiled firmware against the host-built libsafety on the same test vectors, plus HIL. | Not Started
cppcheck MISRA addon | Cppcheck project | As pinned by opendbc | MISRA C:2012 checking of safety code | TCL2 (provisional) | TI2: a missed violation could hide a defect. TD2: code review and unit tests also catch most defects such a rule targets. | Not Started
Python unittest + libsafety harness | opendbc (upstream) | opendbc 229dc70 | Unit tests of brand safety modes; source of coverage data | TCL2 (provisional) | TI2: a harness bug could report a false pass. TD2: mutation testing checks that the tests detect injected faults. | Not Started
gcov | GNU | With the host gcc | Structural coverage of the safety layer | TCL2 (provisional) | TI2: overstated coverage could hide untested code. TD2: cross-checked by mutation analysis and the independent XZACT equivalence coverage report. | Not Started
Mutation test harness (opendbc test_mutation.py) | opendbc (upstream) | opendbc 229dc70 | Checks that the safety tests detect injected faults | TCL1 | TI1 for the product: it can only report weak tests, not introduce or hide a product defect. | Not Required
XZACT compiler and equivalence harness | XZACT-Lang (jherrodthomas) | 0.9.3, branch claude/admiring-ritchie-hneag0 | Independent re-implementation of the Toyota safety mode, used as diverse evidence of its behavior | TCL1 | TI1 while used only as independent evidence: a fault in the port or compiler causes a mismatch against the original C, not a hidden product defect. Becomes TCL3 if XZACT-generated code is ever used in the product; known silent-miscompile issues would then block it. | Not Required
openpilot process replay | comma.ai (upstream) | As pinned | Regression detection by replaying recorded drives | TCL2 (provisional) | TI2: a false 'no change' result could let a regression through. TD2: complemented by unit tests and on-road validation. | Not Started
tinygrad | tinygrad (upstream) | As pinned | Compiles and runs the driving and driver-monitoring models | To be determined | Affects learned components argued under ISO 21448 and ISO/PAS 8800; classification depends on the TSC independence argument. | Not Started
SCons, GitHub Actions, Jenkins | Various | As configured | Build orchestration and CI | TCL1 | TI1 for the product: build and CI faults surface as build or test failures, verified by checksums and test results. | Not Required
Git and GitHub | GitHub | Hosted | Configuration management, review, traceability of changes | TCL1 | Supports configuration management (26262-8 §7); does not produce product content. | Not Required

## 08_Resources
Resources
Resource Category | Description | Status
Hardware Resources | comma device, panda, Toyota harness; 2020 Toyota Corolla LE reference vehicle. Needed: HIL bench (panda + CAN simulation) for firmware-level testing. | Partially available
Software Tool Licenses | None required: the toolchain is open source (see 07_Tools). Commercial tools, if adopted (e.g. requirements management), will be listed here. | N/A
Lab Equipment | CAN interface and logger for vehicle measurements; steering torque measurement for assumption ASM-V-02; access to a closed test track for validation. | Not available
Training Plan | ISO 26262 and ISO 21448 orientation for every contributor touching a safety-related element; reviewer onboarding to the change workflow in docs/safety/README.md. | Not started

## 09_Anomaly_Resolution
Anomaly Resolution Process
Process: Anomalies are tracked as GitHub issues labelled 'safety-anomaly' and mirrored here at each plan revision. Each is assessed for impact on safety goals, requirements and evidence (ISO 26262-8 §8), assigned an owner, and closed only with linked evidence. An anomaly that affects a released work product reopens that work product's confirmation review.
ID | Raised By | Date Raised | Description | Severity | Owner | Status | Resolution
A01 | Jherrod Thomas | 2026-10-09 | No independent reviewers: ASIL D work products need I3 confirmation reviews, and the project has a single maintainer. | Major | Jherrod Thomas | Open | Recruit independent reviewers (milestone M05). Until then no confirmation review can close.
A02 | Claude Code (equivalence work) | 2026-10-09 | The XZACT compiler silently miscompiled valid programs (Otherwise bound to a nested If; shared text buffers; out-of-order top-level Let). See XZACT-Lang apps/openpilot_toyota_safety/README.md. | Minor | Jherrod Thomas | Open | No product impact while XZACT is used only as independent evidence (TCL1): a miscompile shows up as a mismatch. Blocks any use of XZACT-generated code in the product.
A03 | Claude Code (planning) | 2026-10-09 | No development interface agreement is possible with upstream (comma.ai). Upstream changes arrive through submodule pins without a supplier safety case. | Major | Jherrod Thomas | Open | Treat upstream as existing software (ISO 26262-8 §12): pin commits, impact-analyze every pin update, and qualify the safety layer with LionDriver's own evidence.
A04 | Claude Code (planning) | 2026-10-09 | Target ASIL D is a planning assumption made before the HARA. | Minor | Jherrod Thomas | Open | Draft HARA LD-HARA-001 0.1 yields five ASIL D safety goals (SG-001 to SG-005), consistent with the target. Closes when the HARA passes its confirmation review.
A05 | Claude Code (FSC) | 2026-10-10 | panda microcontroller fault detection is insufficient for ASIL D: a software watchdog on the main loop and interrupt-rate monitoring only record faults; no lockstep core or independent hardware watchdog; no evidence that a recorded fault leads to a no-output state (FSC gap G1). | Major | Hardware Lead (vacant) | Open | Assess the STM32H7's safety mechanisms; decide on an external watchdog with relay cut-off and/or a second monitoring MCU in the TSC. Blocks the D(D) + QM(D) decomposition.

## 10_Schedule
Project Schedule
Milestone ID | Milestone Name | Target Date | Predecessors | Status | Notes
M01 | Safety framework published | 2026-Q4 |  | In Progress | README, docs/safety framework, standards mapping (LionDriver PR #1)
M02 | Safety plan draft | 2026-Q4 | M01 | In Progress | This document
M03 | Operating envelope decided | 2026-Q4 | M01 | Completed | Envelope confirmed by the maintainer on 2026-10-09
M04 | Item definition and HARA drafted | 2026-Q4 | M03 | In Progress | Drafts 0.1 of LD-ITD-001 and LD-HARA-001 complete; awaiting review
M05 | Independent reviewers recruited | 2027-Q1 | M02 | Not Started | Blocking: no confirmation review can close without them
M06 | Functional safety concept, SOTIF and TARA drafted | 2027-Q1 | M04 | In Progress | FSC draft 0.1 complete; SOTIF and TARA not started
M07 | Technical safety concept and existing-software assessment | 2027-Q2 | M06 | Not Started | Includes the doer/checker independence argument
M08 | Safety-layer verification and HIL | 2027-Q3 | M07 | Not Started | Builds on the Toyota equivalence evidence
M09 | Corolla configuration validated | 2027-Q4 | M08 | Not Started | Assumption checks on the vehicle, track testing
M10 | Safety case and independent assessment | 2028-Q1 | M09, M05 | Not Started

## 11_References
References
Reference | Title | Notes
ISO 26262-1 to -12:2018 | Road vehicles — Functional safety | Parts 2–6, 8–10 applied; 5 and 11 partial; 7 and 12 not applicable (see 04_Tailoring)
ISO 21448:2022 | Road vehicles — Safety of the intended functionality | Perception, planning, operating envelope
ISO/SAE 21434:2021 | Road vehicles — Cybersecurity engineering | TARA, cybersecurity goals and concept
ISO/PAS 8800:2024 | Road vehicles — Safety and artificial intelligence | Driving and driver-monitoring models
UL 4600 (3rd ed.) | Evaluation of autonomous products | Safety-case structure and safety performance indicators, where applicable
ISO 11270 | Lane keeping assistance systems | Lateral limits enforced by the safety layer
ISO 15622 | Adaptive cruise control systems | Longitudinal limits
UN R79 · UN R171 | Steering equipment · Driver Control Assistance Systems | Regulatory context
MISRA C:2012 | Guidelines for the use of C in critical systems | Safety-layer firmware
docs/safety/README.md | LionDriver safety framework, work-product index and change workflow | This repository
docs/safety/standards.md | How LionDriver applies the standards | This repository
docs/safety/platform/README.md | Platform item definition outline, operating envelope, assumptions register | This repository