## Title
Safety Plan Confirmation Measures Checklist
WP-M-02 Functional safety plan
| Project Number & Name | LionDriver
| Item / Component | LionDriver Supervised Driving Assistance (LD-SDA), reference configuration
| Document Title | Confirmation Measures - Safety Plan
| Safety Plan Revision | 0.1
| Safety Plan Status | Draft
| Target ASIL | All. Planned to ASIL D until the HARA (WP-C-03) is approved
| Source Safety Plan | WP-M-02-safety-plan.xlsx
| Checklist Generated | 2026-10-10
| Standard | ISO 26262:2018 Part 2 §6 (Safety Plan planning and confirmation)
| Reviewer | (to be assigned — independence per ISO 26262-2 Table 1)

## General Info
General Information
Tabs in this Checklist
Tab | Purpose
Title | Safety Plan being assessed and reviewer info
General Info | This tab — TOC and document conventions
Guide | How to interpret ratings and use the checklist
Summary | Statistical roll-up of findings
Confirmation Review | Generic doc-quality checks (ISO 26262-8 §10)
Safety Plan Assessment | Safety Plan substantive checks (ISO 26262-2 §6)
Verification Assessment | Verification planning checks (ISO 26262-8 §9)
References
ID | Title
Ref-1 | ISO 26262:2018 — Road vehicles - Functional safety
Ref-2 | ISO 26262-2:2018 clause 6 — Safety Planning
Ref-3 | Source Safety Plan workbook — see Title tab

## Guide
Guide — How to Use This Checklist
# | Instruction
1 | Each check has an Assessment column. Possible values: FC (Fully Compliant), LC (Largely Compliant), PC (Partially Compliant), NO (Not Compliant), NA (Not Applicable), or blank (pending).
2 | Findings cells contain evidence the auto-reviewer found in the source Safety Plan. Cells marked '(Auto-suggest, requires reviewer judgment)' need a human pass.
3 | Page/Section cells reference where in the source Safety Plan the evidence lives.
4 | Recommended Actions cells contain corrective actions for non-compliances. They do NOT modify the source — analyst decides whether to update and re-run.
5 | Confidence column: High = directly verified; Medium = inferred with caveat; Low = subjective or external artifact required.
6 | Obligation: Shall = mandatory; Should = recommended. NO on a Shall is major; on a Should is minor non-conformance.
7 | The Summary tab rolls up counts. Update Assessment and Summary recomputes.
8 | The reviewer is responsible for final judgment. ISO 26262-2 requires confirmation reviews with I1/I2/I3 independence per ASIL.

## Summary
Safety Plan Confirmation Measures — Dashboard
LionDriver
Total Items |  |  |  |  | Compliance % |  | Pending Review | Major Issues | Fully Compliant | 14 | CR | 64.2857
34 |  |  |  |  | 47% |  | 13 | 1 | Largely Compliant | 2 | SPA | 50
[9 empty] | Partially Compliant | 4 | VA | 0
[9 empty] | Not Compliant | 1
OVERALL STATUS: REJECTED | [8 empty] | Pending Review | 13
[11 empty] | Section | Fully Compliant | Largely Compliant | Partially Compliant | Not Compliant | Not Applicable | Pending Review
[11 empty] | CR: Document Quality | 9 | 0 | 0 | 0 | 0 | 5
[11 empty] | SPA: Planning Organization | 0 | 1 | 0 | 1 | 0 | 0
[11 empty] | SPA: Planning Tailoring | 1 | 0 | 0 | 0 | 0 | 0
[11 empty] | SPA: Work Products | 0 | 1 | 3 | 0 | 0 | 0
[11 empty] | SPA: Confirmation Reviews | 1 | 0 | 1 | 0 | 0 | 0
[11 empty] | SPA: Tools and Qualification | 2 | 0 | 0 | 0 | 0 | 0
[11 empty] | SPA: Process Definition | 0 | 0 | 0 | 0 | 0 | 1
[11 empty] | SPA: Schedule | 1 | 0 | 0 | 0 | 0 | 0
[11 empty] | SPA: References | 0 | 0 | 0 | 0 | 0 | 1
[11 empty] | VA: Verification Planning | 0 | 0 | 0 | 0 | 0 | 2
[11 empty] | VA: Verification Specification | 0 | 0 | 0 | 0 | 0 | 2
[11 empty] | VA: Verification Execution | 0 | 0 | 0 | 0 | 0 | 2
Findings — Non-Conformances and Partial Compliance
Tab | ID | Obligation | Rating | Requirement | Finding | Recommended Action
SPA | 1 | Shall | NO | Is the Functional Safety Manager assigned and identified? | No Functional Safety Manager role identified. | Assign a Functional Safety Manager and document in Roles & Responsibilities tab.
SPA | 5 | Shall | PC | Does each work product have an assigned owner? | Only 0/85 work products have assigned owners. | Assign a responsible person/team to each work product.
SPA | 6 | Shall | PC | Does each work product have a planned completion date? | Only 0/85 work products have planned dates. | Define planned completion dates for all work products.
SPA | 7 | Shall | PC | Does each work product have a target ASIL specified? | Only 0/85 work products have target ASIL. | Specify the target ASIL for each work product per ISO 26262-2:2018 clause 6.4.1.
SPA | 8 | Shall | PC | Is confirmation review planned for every safety-relevant work product? | Only 12 of 85 work products have CRs planned. | Plan confirmation reviews for all safety-relevant work products per ISO 26262-2:2018 clause 6.4.7.

## Confirmation Review
Confirmation Review
ID | Section | Requirement | Obligation | Assessment | Findings | Page/Section | Recommended Actions
Document Quality
1 | Document Quality | Is the document structured in a clear manner? | Shall | FC | Safety Plan structured into 12 tabs with distinct sections. | All tabs
2 | Document Quality | Was the latest template used when the document was created? | Should | — | (Auto-suggest, requires reviewer judgment) Template version cannot be detected from xlsx content alone. |  | Confirm the latest applicable Safety Plan template was used at document creation.
3 | Document Quality | Does the document structure facilitate search for relevant information? | Should | FC | Document has structured tab naming (0x_Prefix_Name format); structured columns aid search. | Sheets: ['00_Title_Page', '01_Document_Control', '02_Project_Info']
4a | Document Quality | Does the title cover the scope of the content? | Shall | — | (Auto-suggest, requires reviewer judgment) Title is: 'WP-M-02 Functional safety plan'. Reviewer to confirm it covers the document scope. | Title page row 2 | (Reviewer to verify and assess)
4b | Document Quality | Are the author and approver(s) listed? | Shall | FC | Author='Assurance team (initial draft)', Approver='Safety manager' both populated on Title page. | Title page
4c | Document Quality | Is there a unique identification for each revision? | Shall | FC | Revision='0.1' is set on the Title page. | Title page Revision field
4d | Document Quality | Is there a change history available? | Shall | FC | Safety-plan-builder format includes Document Control tab for revision history. | 01_Document_Control
4e | Document Quality | Is the status of the work product provided? | Shall | FC | Status='Draft' is set on the Title page. | Title page Status field
5 | Document Quality | Is the current applicable revision clearly identifiable? | Shall | FC | Current revision '0.1' is identifiable on Title page. | Title page Revision field
6 | Document Quality | Is the document under configuration and change management? | Shall | — | (Auto-suggest, requires reviewer judgment) Configuration management is an organizational practice; cannot be verified from xlsx content. |  | Confirm the document is checked into the project's configuration-management system (e.g., Polarion, DOORS, Git).
7 | Document Quality | Are the header and footer updated? | Should | — | (Auto-suggest, requires reviewer judgment) Worksheet headers/footers cannot be reliably verified programmatically. |  | Open the workbook in Excel and confirm header/footer reflect current document ID and revision.
8 | Document Quality | Does this document contain a correct table of contents? | Shall | FC | Document has numbered tabs (0x_Name format) that function as table of contents. | Sheet structure starting with '00_Title_Page'
9 | Document Quality | Does the Reference Table list all references in the Work Product? | Should | — | (Auto-suggest, requires reviewer judgment) References-style content found on sheet '11_References'. Reviewer to confirm completeness. | Sheet '11_References' | (Reviewer to verify and assess)
10 | Document Quality | Have all sections of the Work Product been completed? | Should | FC | Safety Plan has 4/4 critical sections populated.

## Safety Plan Assessment
Safety Plan Assessment
ID | Section | Requirement | Obligation | Assessment | Findings | Page/Section | Recommended Actions
Planning Organization
1 | Planning Organization | Is the Functional Safety Manager assigned and identified? | Shall | NO | No Functional Safety Manager role identified. |  | Assign a Functional Safety Manager and document in Roles & Responsibilities tab.
2 | Planning Organization | Are roles and responsibilities defined for all key positions? | Shall | LC | 14 roles defined; some key roles may be missing. |  | Ensure FSM, Project Manager, Hardware Lead, and Software Lead are assigned.
Planning Tailoring
3 | Planning Tailoring | Are tailoring justifications documented where applicable? | Shall | FC | All 13 tailoring decisions justified. | 04_Tailoring
Work Products
4 | Work Products | Is the list of safety-relevant work products complete? | Shall | LC | 85 work products listed. |  | Ensure HARA, Functional Safety Concept, Technical Safety Concept, and Safety Case are included.
5 | Work Products | Does each work product have an assigned owner? | Shall | PC | Only 0/85 work products have assigned owners. |  | Assign a responsible person/team to each work product.
6 | Work Products | Does each work product have a planned completion date? | Shall | PC | Only 0/85 work products have planned dates. |  | Define planned completion dates for all work products.
7 | Work Products | Does each work product have a target ASIL specified? | Shall | PC | Only 0/85 work products have target ASIL. |  | Specify the target ASIL for each work product per ISO 26262-2:2018 clause 6.4.1.
Confirmation Reviews
8 | Confirmation Reviews | Is confirmation review planned for every safety-relevant work product? | Shall | PC | Only 12 of 85 work products have CRs planned. |  | Plan confirmation reviews for all safety-relevant work products per ISO 26262-2:2018 clause 6.4.7.
9 | Confirmation Reviews | Does confirmation review independence match required ASIL level? | Shall | FC | All 12 confirmation reviews have independence level matching ASIL. | 06_Confirmation_Reviews
Tools and Qualification
10 | Tools and Qualification | Are all tools listed with TCL classification? | Shall | FC | All 22 tools have TCL classification. | 07_Tools, TCL column
11 | Tools and Qualification | Is qualification status documented for TCL2/TCL3 tools? | Shall | FC | All 9 TCL2/TCL3 tools have qualification status documented. | 07_Tools, Qualification Status column
Process Definition
12 | Process Definition | Is the anomaly resolution process described? | Shall | — | (Auto-suggest, requires reviewer judgment) Anomaly resolution process documented in a dedicated tab. Reviewer to verify completeness. | 09_Anomaly_Resolution or similar | (Reviewer to verify and assess)
Schedule
13 | Schedule | Are safety-critical schedule milestones defined? | Shall | FC | 7 milestones defined in the Safety Plan schedule. | 10_Schedule
References
14 | References | Are applicable ISO 26262 parts and standards referenced? | Shall | — | (Auto-suggest, requires reviewer judgment) References documented on sheet '11_References'. Reviewer to verify ISO 26262 citations. | Sheet '11_References' | (Reviewer to verify and assess)

## Verification Assessment
Verification Assessment
ID | Section | Requirement | Obligation | Assessment | Findings | Page/Section | Recommended Actions
Verification Planning
1 | Verification Planning | Does the Verification Plan ensure compliance with Safety Plan? | Shall | — | (Auto-suggest, requires reviewer judgment) Verification Plan ensuring compliance with Safety Plan is governed by an external Verification Plan / Report — not in the Safety Plan xlsx. |  | Verify against the project's Verification Plan and Report documents.
2 | Verification Planning | Are verification methods and tools specified? | Shall | — | (Auto-suggest, requires reviewer judgment) Verification methods and tools specified is governed by an external Verification Plan / Report — not in the Safety Plan xlsx. |  | Verify against the project's Verification Plan and Report documents.
Verification Specification
3 | Verification Specification | Are pass/fail criteria defined for each activity? | Shall | — | (Auto-suggest, requires reviewer judgment) Pass/fail criteria defined for each verification activity is governed by an external Verification Plan / Report — not in the Safety Plan xlsx. |  | Verify against the project's Verification Plan and Report documents.
4 | Verification Specification | Is the verification environment specified? | Shall | — | (Auto-suggest, requires reviewer judgment) Verification environment (lab, sim, vehicle) specified is governed by an external Verification Plan / Report — not in the Safety Plan xlsx. |  | Verify against the project's Verification Plan and Report documents.
Verification Execution
5 | Verification Execution | Is the anomaly handling process defined? | Shall | — | (Auto-suggest, requires reviewer judgment) Anomaly handling process for verification deviations is governed by an external Verification Plan / Report — not in the Safety Plan xlsx. |  | Verify against the project's Verification Plan and Report documents.
6 | Verification Execution | Is a regression testing strategy documented? | Shall | — | (Auto-suggest, requires reviewer judgment) Regression testing strategy upon changes is governed by an external Verification Plan / Report — not in the Safety Plan xlsx. |  | Verify against the project's Verification Plan and Report documents.