## Title
TSC Confirmation Measures Checklist
Technical Safety Concept (TSC): WP-S-02 TSRs, WP-S-03 architecture, WP-S-04 timing, WP-S-05 HSI, WP-A-03 DFA, WP-A-04 FMEA
| Project | LionDriver
| TSC Document ID | WP-S-02 / WP-S-03 (with WP-S-04, WP-S-05, WP-A-03, WP-A-04)
| Document Title | Confirmation Measures - TSC (Technical Safety Concept)
| TSC Revision | WP-S-02 0.2; WP-S-03 0.2; WP-A-03/04 0.2; WP-S-04/05 0.1
| TSC Status | Draft
| Source TSC | out/LionDriver-TSC.xlsx
| Linked FSC | WP-C-04 v0.2
| Checklist Generated | 2026-10-12
| Standard | ISO 26262:2018 Part 4 (System Level), Part 8 §9 (Verification), Part 9 §7 (DFA)
| Reviewer | (to be assigned — independence per ISO 26262-2 Table 1)

## General Info
General Information
Tabs in this Checklist
Tab | Purpose
Title | TSC being assessed and reviewer info
General Info | This tab — TOC and document conventions
Guide | How to interpret ratings
Summary | Visual dashboard with charts and findings
Confirmation Review | Generic doc-quality checks (ISO 26262-8 §10)
Technical Safety Assessment | TSC substantive checks (ISO 26262-4)
Verification Assessment | Verification checks (ISO 26262-8 §9 plus TSC-specific)

## Guide
Guide — How to Use This Checklist
# | Instruction
1 | Each check has an Assessment column. Possible values: FC, LC, PC, NO, NA, or blank (pending).
2 | Findings cells contain evidence the auto-reviewer found in the source TSC. Cells marked '(Auto-suggest)' need a human pass.
3 | Recommended Actions cells contain corrective actions. The skill does NOT modify the source TSC.
4 | Confidence: High = directly verified; Medium = inferred; Low = subjective or external.
5 | Obligation: Shall = mandatory; Should = recommended. NO on Shall = major non-conformance.
6 | Summary tab is a visual dashboard with KPI tiles, pie chart of rating distribution, bar chart of compliance % by tab, stacked bar of section-level breakdown, and a findings table.
7 | Acceptance of the TSC requires no major non-conformances and (when decomposition was applied in FSC) populated DFA.

## Summary
TSC Confirmation Measures — Dashboard
LionDriver
Total Items |  |  |  |  | Compliance % |  | Pending Review | Major Issues | Fully Compliant | 22 | CR | 64.2857
63 |  |  |  |  | 35% |  | 33 | 1 | Partially Compliant | 7 | TSA | 66.6667
[9 empty] | Not Compliant | 1 | VA | 8.8235
[9 empty] | Pending Review | 33
OVERALL STATUS: REJECTED
[11 empty] | Section | Fully Compliant | Largely Compliant | Partially Compliant | Not Compliant | Not Applicable | Pending Review
[11 empty] | CR: Document Quality | 9 | 0 | 1 | 0 | 0 | 4
[11 empty] | TSA: Prerequisites | 1 | 0 | 0 | 0 | 0 | 0
[11 empty] | TSA: Architecture | 1 | 0 | 0 | 0 | 0 | 0
[11 empty] | TSA: TSR Derivation | 0 | 0 | 2 | 0 | 0 | 0
[11 empty] | TSA: TSR Allocation | 1 | 0 | 0 | 0 | 0 | 0
[11 empty] | TSA: Safety Mechanisms | 1 | 0 | 1 | 0 | 0 | 0
[11 empty] | TSA: HW-SW Interface | 0 | 0 | 0 | 1 | 0 | 0
[11 empty] | TSA: Timing Budget | 0 | 0 | 1 | 0 | 0 | 0
[11 empty] | TSA: System FMEA | 1 | 0 | 0 | 0 | 0 | 0
[11 empty] | TSA: Dependent Failure Analysis | 1 | 0 | 0 | 0 | 0 | 0
[11 empty] | TSA: Verification Planning | 1 | 0 | 0 | 0 | 0 | 0
[11 empty] | TSA: HW Hand-off | 1 | 0 | 0 | 0 | 0 | 0
[11 empty] | TSA: SW Hand-off | 1 | 0 | 0 | 0 | 0 | 0
[11 empty] | TSA: ASIL Consistency | 1 | 0 | 0 | 0 | 0 | 0
[11 empty] | VA: Verification Planning | 0 | 0 | 0 | 0 | 0 | 15
[11 empty] | VA: Verification Specification | 0 | 0 | 0 | 0 | 0 | 12
[11 empty] | VA: Verification Execution | 0 | 0 | 0 | 0 | 0 | 2
[11 empty] | VA: TSC-Specific Verification | 3 | 0 | 2 | 0 | 0 | 0
Findings — Non-Conformances and Partial Compliance
Tab | ID | Obligation | Rating | Requirement | Finding | Recommended Action
CR | 10 | Should | PC | All sections completed? | TSRs 100%; HSI 0%. | Complete remaining TSR text and HSI encoding fields.
TSA | 3 | Shall | PC | Has at least one HW-TSR been derived for each FSR? | 1/54 FSRs have HW-TSRs. | Derive HW-TSR for uncovered FSRs.
TSA | 4 | Shall | PC | Has at least one SW-TSR been derived for each FSR? | 53/54 FSRs have SW-TSRs. | Derive SW-TSR for uncovered FSRs.
TSA | 6 | Shall | PC | Has a safety mechanism been chosen for each FSR? | 50/54 FSRs have a primary mechanism. | Select a primary mechanism for each FSR.
TSA | 8 | Shall | NO | Has the HSI been specified for safety mechanisms crossing the HW/SW boundary? | No HSI signals defined. | Define HSI signals for all safety mechanisms crossing HW/SW boundary.
TSA | 9 | Shall | PC | Has FTTI been split into FDTI and FRTI for each FSR? | 49/54 FSRs have FDTI/FRTI populated. Others need FTTI from parent FSC. | Populate FTTI for FSRs left as <TBD>; the 50/50 split will then auto-populate.
VA | 33a | Shall | PC | Completeness with regard to FSRs (every FSR addressed by TSC)? | TSC covers 53/54 FSRs. | Derive TSRs for uncovered FSRs.
VA | 33d | Shall | PC | Completeness of TSR coverage? | TSC covers 53/54 FSRs. | Derive TSRs for uncovered FSRs.

## Confirmation Review
Confirmation Review
ID | Section | Requirement | Obligation | Assessment | Findings | Page/Section in TSC | Recommended Actions
Document Quality
1 | Document Quality | Is the document structured in a clear manner? | Shall | FC | Document is structured into 13 tabs.
2 | Document Quality | Was the latest template available used? | Should | — | (Auto-suggest, requires reviewer judgment) Template version cannot be detected from xlsx content. |  | Confirm latest TSC template was used.
3 | Document Quality | Does the structure facilitate information search? | Should | FC | Title/Contents tab present.
4a | Document Quality | Does the title cover the scope? | Shall | — | (Auto-suggest, requires reviewer judgment) Title is: 'Technical Safety Concept (TSC): WP-S-02 TSRs, WP-S-03 architecture, WP-S-04 timing, WP-S-05 HSI, WP-A-03 DFA, WP-A-04 FMEA'. Reviewer to confirm scope coverage. | Title page | (Reviewer to verify and assess)
4b | Document Quality | Are author and approver(s) listed? | Shall | FC | Author='Assurance team (initial draft)', Approver='Safety manager'.
4c | Document Quality | Unique identification per revision? | Shall | FC | Revision='WP-S-02 0.2; WP-S-03 0.2; WP-A-03/04 0.2; WP-S-04/05 0.1'.
4d | Document Quality | Change history available? | Shall | FC | Revision history has 2 rows.
4e | Document Quality | Status of work product provided? | Shall | FC | Status='Draft'.
5 | Document Quality | Current applicable revision identifiable? | Shall | FC | Current revision='WP-S-02 0.2; WP-S-03 0.2; WP-A-03/04 0.2; WP-S-04/05 0.1'.
6 | Document Quality | Document under configuration management? | Shall | — | (Auto-suggest, requires reviewer judgment) Configuration management is organizational. |  | Confirm document is in CM system.
7 | Document Quality | Header and footer updated? | Should | — | (Auto-suggest, requires reviewer judgment) Header/footer not reliably accessible. |  | Open in Excel; verify.
8 | Document Quality | Correct table of content? | Shall | FC | TOC tab present.
9 | Document Quality | Reference Table lists all references? | Should | FC | Linked FSC referenced: WP-C-04 v0.2.
10 | Document Quality | All sections completed? | Should | PC | TSRs 100%; HSI 0%. |  | Complete remaining TSR text and HSI encoding fields.

## Technical Safety Assessment
Technical Safety Assessment
ID | Section | Requirement | Obligation | Assessment | Findings | Page/Section in TSC | Recommended Actions
Prerequisites
1 | Prerequisites | Is the FSC available with FSRs derived? | Shall | FC | FSC prerequisite met: 54 FSRs imported. | Sheet '02_FSRs_From_FSC'
Architecture
2 | Architecture | Has the system architecture been refined into HW components and SW partitions? | Shall | FC | Architecture refined: 3 HW components and 4 SW partitions. | Sheet '03_System_Architecture'
TSR Derivation
3 | TSR Derivation | Has at least one HW-TSR been derived for each FSR? | Shall | PC | 1/54 FSRs have HW-TSRs. |  | Derive HW-TSR for uncovered FSRs.
4 | TSR Derivation | Has at least one SW-TSR been derived for each FSR? | Shall | PC | 53/54 FSRs have SW-TSRs. |  | Derive SW-TSR for uncovered FSRs.
TSR Allocation
5 | TSR Allocation | Has each TSR been allocated to a HW or SW element? | Shall | FC | All 148 TSRs allocated to a node/element.
Safety Mechanisms
6 | Safety Mechanisms | Has a safety mechanism been chosen for each FSR? | Shall | PC | 50/54 FSRs have a primary mechanism. |  | Select a primary mechanism for each FSR.
7 | Safety Mechanisms | Are diagnostic coverage targets specified for each safety mechanism? | Shall | FC | All 87 mechanism rows have DC% targets.
HW-SW Interface
8 | HW-SW Interface | Has the HSI been specified for safety mechanisms crossing the HW/SW boundary? | Shall | NO | No HSI signals defined. |  | Define HSI signals for all safety mechanisms crossing HW/SW boundary.
Timing Budget
9 | Timing Budget | Has FTTI been split into FDTI and FRTI for each FSR? | Shall | PC | 49/54 FSRs have FDTI/FRTI populated. Others need FTTI from parent FSC. |  | Populate FTTI for FSRs left as <TBD>; the 50/50 split will then auto-populate.
System FMEA
10 | System FMEA | Has system-level FMEA been performed? | Shall | FC | System FMEA scaffold present with 40 rows. | Sheet '08_System_FMEA'
Dependent Failure Analysis
11 | Dependent Failure Analysis | If decomposition was applied in FSC, has DFA been performed for each decomposed pair? | Shall | FC | DFA scaffold present with 7 rows; 7 populated.
Verification Planning
12 | Verification Planning | Have verification methods been specified for each TSR? | Shall | FC | All 148 TSRs have verification methods specified. | Sheet '10_Verification'
HW Hand-off
13 | HW Hand-off | Has the HW hand-off (Part 5) been prepared? | Shall | FC | HW hand-off tab present: '11_HW_Handoff'.
SW Hand-off
14 | SW Hand-off | Has the SW hand-off (Part 6) been prepared? | Shall | FC | SW hand-off tab present: '12_SW_Handoff'.
ASIL Consistency
15 | ASIL Consistency | Are TSR allocated ASILs consistent with parent FSR ASILs (decomposition can lower; never raise)? | Shall | FC | All TSR allocated ASILs are ≤ parent FSR ASIL (decomposition can lower; never raise).

## Verification Assessment
Verification Assessment
ID | Section | Requirement | Obligation | Assessment | Findings | Page/Section in TSC | Recommended Actions
Verification Planning
24 | Verification Planning | Plan ensures compliance with TSC? | Shall | — | (Auto-suggest, requires reviewer judgment) Verification Plan compliance with TSC is governed by an external Verification Plan / Specification / Report. |  | Verify against project verification documents.
25 | Verification Planning | Safety Validation refined based on TSRs? | Should | — | (Auto-suggest, requires reviewer judgment) Safety Validation refinement based on TSRs is part of validation planning. |  | (Reviewer to verify and assess)
26 | Verification Planning | Plan addresses content/methods/criteria/env/tools/anomalies/regression? | Shall | — | (Auto-suggest, requires reviewer judgment) Plan addresses content/methods/criteria/env/tools/anomalies/regression is governed by an external Verification Plan / Specification / Report. |  | Verify against project verification documents.
26a | Verification Planning | Plan content? | Shall | — | (Auto-suggest, requires reviewer judgment) Plan content is governed by an external Verification Plan / Specification / Report. |  | Verify against project verification documents.
26b | Verification Planning | Methods? | Shall | — | (Auto-suggest, requires reviewer judgment) Methods is governed by an external Verification Plan / Specification / Report. |  | Verify against project verification documents.
26c | Verification Planning | Pass/fail? | Shall | — | (Auto-suggest, requires reviewer judgment) Pass/fail is governed by an external Verification Plan / Specification / Report. |  | Verify against project verification documents.
26d | Verification Planning | Environment? | Shall | — | (Auto-suggest, requires reviewer judgment) Environment is governed by an external Verification Plan / Specification / Report. |  | Verify against project verification documents.
26e | Verification Planning | Tools? | Shall | — | (Auto-suggest, requires reviewer judgment) Tools is governed by an external Verification Plan / Specification / Report. |  | Verify against project verification documents.
26f | Verification Planning | Anomalies? | Shall | — | (Auto-suggest, requires reviewer judgment) Anomalies is governed by an external Verification Plan / Specification / Report. |  | Verify against project verification documents.
26g | Verification Planning | Regression? | Shall | — | (Auto-suggest, requires reviewer judgment) Regression is governed by an external Verification Plan / Specification / Report. |  | Verify against project verification documents.
27 | Verification Planning | Planning considers method adequacy / complexity / experience / maturity? | Should | — | (Auto-suggest, requires reviewer judgment) Planning considerations is governed by an external Verification Plan / Specification / Report. |  | Verify against project verification documents.
27a | Verification Planning | Method adequacy? | Should | — | (Auto-suggest, requires reviewer judgment) Method adequacy is governed by an external Verification Plan / Specification / Report. |  | Verify against project verification documents.
27b | Verification Planning | Complexity? | Should | — | (Auto-suggest, requires reviewer judgment) Complexity is governed by an external Verification Plan / Specification / Report. |  | Verify against project verification documents.
27c | Verification Planning | Prior experience? | Should | — | (Auto-suggest, requires reviewer judgment) Prior experience is governed by an external Verification Plan / Specification / Report. |  | Verify against project verification documents.
27d | Verification Planning | Technology maturity? | Should | — | (Auto-suggest, requires reviewer judgment) Technology maturity is governed by an external Verification Plan / Specification / Report. |  | Verify against project verification documents.
Verification Specification
28 | Verification Specification | Methods specified (review/sim/test)? | Shall | — | (Auto-suggest, requires reviewer judgment) Verification methods specified is governed by an external Verification Plan / Specification / Report. |  | Verify against project verification documents.
28a | Verification Specification | Review checklists? | Shall | — | (Auto-suggest, requires reviewer judgment) Review/analysis checklists (e.g., this skill's output) is governed by an external Verification Plan / Specification / Report. |  | Verify against project verification documents.
28b | Verification Specification | Simulation? | Shall | — | (Auto-suggest, requires reviewer judgment) Simulation scenarios is governed by an external Verification Plan / Specification / Report. |  | Verify against project verification documents.
28c | Verification Specification | Test cases? | Shall | — | (Auto-suggest, requires reviewer judgment) Test cases is governed by an external Verification Plan / Specification / Report. |  | Verify against project verification documents.
29 | Verification Specification | Test case content? | Shall | — | (Auto-suggest, requires reviewer judgment) Test case content is governed by an external Verification Plan / Specification / Report. |  | Verify against project verification documents.
29a | Verification Specification | Unique ID? | Shall | — | (Auto-suggest, requires reviewer judgment) Unique ID is governed by an external Verification Plan / Specification / Report. |  | Verify against project verification documents.
29b | Verification Specification | Version ref? | Shall | — | (Auto-suggest, requires reviewer judgment) Version reference is governed by an external Verification Plan / Specification / Report. |  | Verify against project verification documents.
29c | Verification Specification | Preconditions? | Shall | — | (Auto-suggest, requires reviewer judgment) Preconditions is governed by an external Verification Plan / Specification / Report. |  | Verify against project verification documents.
29d | Verification Specification | Env conditions? | Shall | — | (Auto-suggest, requires reviewer judgment) Environment is governed by an external Verification Plan / Specification / Report. |  | Verify against project verification documents.
29e | Verification Specification | Inputs? | Shall | — | (Auto-suggest, requires reviewer judgment) Inputs is governed by an external Verification Plan / Specification / Report. |  | Verify against project verification documents.
29f | Verification Specification | Expected behavior? | Shall | — | (Auto-suggest, requires reviewer judgment) Expected behavior is governed by an external Verification Plan / Specification / Report. |  | Verify against project verification documents.
30 | Verification Specification | Test grouping? | Shall | — | (Auto-suggest, requires reviewer judgment) Test grouping is governed by an external Verification Plan / Specification / Report. |  | Verify against project verification documents.
Verification Execution
31 | Verification Execution | Executed per plan? | Shall | — | (Auto-suggest, requires reviewer judgment) Verification executed per plan is governed by an external Verification Plan / Specification / Report. |  | Verify against project verification documents.
32 | Verification Execution | Verification Report content? | Shall | — | (Auto-suggest, requires reviewer judgment) Verification Report is governed by an external Verification Plan / Specification / Report. |  | Verify against project verification documents.
TSC-Specific Verification
33a | TSC-Specific Verification | Completeness with regard to FSRs (every FSR addressed by TSC)? | Shall | PC | TSC covers 53/54 FSRs. |  | Derive TSRs for uncovered FSRs.
33b | TSC-Specific Verification | Compliance with FSC? | Shall | FC | TSC references linked FSC (WP-C-04 v0.2); compliance traced.
33c | TSC-Specific Verification | Consistency with system architecture? | Shall | FC | All FSR-referenced nodes (0) are allocated to HW components or SW partitions.
33d | TSC-Specific Verification | Completeness of TSR coverage? | Shall | PC | TSC covers 53/54 FSRs. |  | Derive TSRs for uncovered FSRs.
33e | TSC-Specific Verification | Consistency of allocated ASILs (TSR <= parent FSR)? | Shall | FC | All TSR allocated ASILs are ≤ parent FSR ASIL (decomposition can lower; never raise).