## Cover
LionDriver · PFM · AIAG-VDA 2019
PFMEA — build, release, install, calibration, OTA
Generated from assurance/08-analyses/fmea/analyses/pfmea.yaml. Do not edit: regenerate with tools/safety/fmea_review_xlsx.py.
Revision | 0.3 · draft
Baseline | BL-003
Rating tables | RT-1
Updated | 2026-10-12
Scope | Release (WP-P-10), installation and provisioning (WP-O-01) and software update/rollback for the reference configuration AC-001, as defined at BL-003. Calibration and fingerprinting are covered as installation steps.
Team | Jherrod Thomas (Project maintainer, safety lead (reviewer/approver)); Claude (AI assistant) (Drafting assistance; ratings require human review)
Summary
Failure modes | 17
Rated causes | 17
AP High | 16
AP Medium | 0
AP Low | 1
Actions (open) | 11 (11)
Legend
H | High: an action or a rationale is required
M | Medium: an action or a rationale is recommended
L | Low
Aa | Amber text: no test targets the cause (detection 9 or 10)
Yellow cells on the Worksheet: reviewer input (decision from the list, comment)
Review sign-off
Reviewer
Independence level
Date
Result (accepted / accepted with findings / rejected)
Findings reference

## Worksheet
FAILURE ANALYSIS (AIAG-VDA STEP 4) | [7 empty] | RISK ANALYSIS (STEP 5) |  |  |  |  | OPTIMIZATION (STEP 6) |  |  |  | REVIEW
Element | Function | Failure effects | Hazards | S | Failure mode | Cause | Failure cause | Prevention controls | O | Detection controls | D | AP | Actions | Status | Revised S/O/D | Revised AP | Reviewer decision | Reviewer comment
PFM-SE-011 R2 Build the release (host tree, panda RELEASE firmware; WP-P-10 §4 step 4, §6) | PFM-FN-002 Produce the release artifacts, including a panda RELEASE build with the LionDriver key and the reference lock | End Envelope can be bypassed or misconfigured End Contributes to HZ-005 End Contributes to HZ-006 Next higher Device runs firmware that accepts any safety mode (and ALLOUTPUT in DEBUG) Local Release artifact built with the wrong flags | HZ-002 HZ-005 HZ-006 | 10 | PFM-001 · wrong_configuration panda firmware released as a DEBUG build, or without LIONDRIVER_REFERENCE | C1 | panda/SConscript defaults to DEBUG with ALLOW_DEBUG; LIONDRIVER_REFERENCE is opt-in and no build path sets it linked: SWF-013 | • WP-P-10 §6 rule (RELEASE=1 with the LionDriver key); not implemented assurance/07-supporting/WP-P-10-release-management.md | 8 | • INS-17 reads the version string (human check); planned release check for RELEASE and absent ALLOW_DEBUG not implemented assurance/09-production-operation/WP-O-01-installation-and-provisioning-control.md | 8 | H | PFM-ACT-001 · design change Make RELEASE=1 LIONDRIVER_REFERENCE=1 with the LionDriver key the only release build, and add an automated release check (version contains RELEASE, ALLOW_DEBUG absent, reference lock present) that blocks publication (WP-P-10 §6; SW FMEA SWF-ACT-009) | open
PFM-SE-011 R2 Build the release (host tree, panda RELEASE firmware; WP-P-10 §4 step 4, §6) | PFM-FN-002 Produce the release artifacts, including a panda RELEASE build with the LionDriver key and the reference lock | End Unverified envelope firmware in the vehicle End Contributes to HZ-005 Next higher Bootstub accepts images that anyone can sign Local Artifact signature not traceable to LionDriver | HZ-002 HZ-005 | 10 | PFM-002 · unverified_artifact panda firmware signed with the debug key or a key not controlled by LionDriver | C1 | No LionDriver release key yet (D-09 decided, not implemented); debug private key is in the repository | • Decision D-09; WP-P-10 §6 key rules assurance/07-supporting/WP-P-10-release-management.md | 8 | • INS-17 compares the signature with the release record (record format not yet in use) assurance/09-production-operation/WP-O-01-installation-and-provisioning-control.md | 8 | H | PFM-ACT-002 · design change Generate the LionDriver release key offline and define the signing procedure (D-09); remove the debug key from release builds | open
PFM-SE-010 R1 Freeze and pin the baseline (WP-P-10 §4 steps 1-3) | PFM-FN-001 Freeze every component of the release at an identified, protected version | End Unverified behaviour of the envelope or controller End Contributes to HZ-005 Next higher Device runs unverified safety code or models Local Baseline manifest does not match what was built | HZ-002 HZ-005 | 10 | PFM-003 · wrong_version A component enters the release at a different version than verified | C1 | Submodule pin moved after verification, or tinygrad tracked by branch | • Submodules pinned by commit on LionDriver forks (D-01); tinygrad by commit • Fork CI runs the safety suite on the pinned submodules .github/workflows/safety.yaml | 3 | • Safety tests, MISRA and mutation run on every change of the pins opendbc_repo/opendbc/safety/tests/test_toyota.py | 4 | L | PFM-ACT-003 · detection Build the HIL bench (D-04) and define the evidence package location and contents (WP-P-10 §5, OI-2) before the first vehicle-test baseline | open
PFM-SE-012 R3 Verify and assemble the evidence package (WP-P-10 §4 steps 5-8, §5) | PFM-FN-003 Run and archive all required verification on the exact release commit | End Undetected defect in a deployed configuration End Contributes to HZ-005 End Contributes to HZ-011 Next higher Release decision taken on partial evidence Local Evidence package incomplete | HZ-002 HZ-005 HZ-011 | 10 | PFM-004 · incomplete Release made without the required verification on the release commit | C1 | No HIL bench or vehicle test capability yet (D-04, GAP-30); evidence package location not defined (WP-P-10 OI-2) | • WP-P-10 §3 gate criteria and §5 evidence package (draft) assurance/07-supporting/WP-P-10-release-management.md | 9 | • Release record review (WP-K-06), human, not yet used assurance/10-safety-case/WP-K-06-release-record.md | 8 | H | PFM-ACT-003 · detection Build the HIL bench (D-04) and define the evidence package location and contents (WP-P-10 §5, OI-2) before the first vehicle-test baseline | open
PFM-SE-013 R4 Release decision and publication (WP-P-10 §4 steps 9-10) | PFM-FN-004 Publish only the approved release through the LionDriver channel | End Unassured configuration driven End Contributes to HZ-005 Next higher Upstream or development software on the device (no reference lock, Experimental default) Local Wrong software source | HZ-002 HZ-005 | 10 | PFM-005 · wrong_version Device installed from the upstream installer or a development branch instead of the LionDriver release | C1 | Installer URL entered by hand; comma's default installer is the natural path; no LionDriver release channel yet | • Procedure defined in a draft work product; no release or third-party installation has been made with it yet assurance/09-production-operation/WP-O-01-installation-and-provisioning-control.md | 8 | • INS-15: installed commit compared with the tag's commit (human check) assurance/09-production-operation/WP-O-01-installation-and-provisioning-control.md | 8 | H | PFM-ACT-004 · design change Set up the LionDriver release channel and an installer that installs only signed release tags and records the installed commit (INS-15) | open
PFM-SE-020 I1 Incoming inspection (WP-O-01 INS-01..04) | PFM-FN-005 Use only the approved, undamaged device and harness | End Stock AEB unavailable or CAN faults while driving End Contributes to HZ-004 Next higher Relay or CAN path faulty from the start Local Harness not the approved type or with damaged pins, latches or relay box | HZ-011 HZ-004 | 10 | PFM-006 · damage Wrong or damaged harness installed | C1 | Visual inspection only; harness revision not recorded against an approved list | • INS-02, INS-03 checklist (draft) assurance/09-production-operation/WP-O-01-installation-and-provisioning-control.md | 7 | • INS-03 visual inspection; INS-14 no relay or CAN alert at first boot assurance/09-production-operation/WP-O-01-installation-and-provisioning-control.md | 8 | H | PFM-ACT-005 · prevention Turn WP-O-01 into a recorded checklist (R-DEV, R-INS) with photos and sign-off, and include harness approval list, latch check and airbag-zone routing diagram for the reference vehicle | open
PFM-SE-021 I2 Vehicle preconditions (INS-05..08) | PFM-FN-006 Install only on a vehicle that is in the reference configuration and healthy | End Safety argument does not hold for this vehicle End Contributes to HZ-011 Next higher Assumptions of use (EPS, PCM, PCS behaviour) no longer valid Local ECU firmware, trim or condition differs from the reference record | HZ-002 HZ-011 | 10 | PFM-007 · wrong_configuration Item installed on a vehicle outside the reference configuration | C1 | Exact ECU firmware compare and DTC read are manual steps; the reference ECU versions are not recorded yet (WP-C-01 OI-1) | • INS-05..08, INS-21 (draft) assurance/09-production-operation/WP-O-01-installation-and-provisioning-control.md | 8 | • INS-21 FW query script output compared by hand with the reference record assurance/09-production-operation/WP-O-01-installation-and-provisioning-control.md | 7 | H | PFM-ACT-006 · detection Write a configuration-check script for INS-18 and INS-21..24 that compares ECU FW versions, model hashes, carParams and pandaStates with the release record and refuses engagement on mismatch (TSR-803) | open
PFM-SE-022 I3 Mechanical and electrical installation (INS-09..14) | PFM-FN-007 Mount the device and connect the harness so that the CAN path, relay and camera view are as designed | End Loss of lateral control or of the stock path while driving End Contributes to HZ-011 Next higher Intermittent CAN or relay drive while driving Local Connector seated but not locked | HZ-004 HZ-011 | 10 | PFM-008 · incomplete Harness connector not fully latched | C1 | Latch engagement judged by feel; no positive check | • INS-11 instruction (draft) assurance/09-production-operation/WP-O-01-installation-and-provisioning-control.md | 7 | • INS-11 pull test by hand; INS-14 alerts at first boot assurance/09-production-operation/WP-O-01-installation-and-provisioning-control.md | 8 | H | PFM-ACT-005 · prevention Turn WP-O-01 into a recorded checklist (R-DEV, R-INS) with photos and sign-off, and include harness approval list, latch check and airbag-zone routing diagram for the reference vehicle | open
PFM-SE-022 I3 Mechanical and electrical installation (INS-09..14) | PFM-FN-007 Mount the device and connect the harness so that the CAN path, relay and camera view are as designed | End Lateral control steers off the lane centre Next higher Small, stable pose error not caught by calibration limits Local Camera pose differs from the calibration assumption | HZ-003 | 10 | PFM-009 · wrong_parameter Device mounted outside the position and attitude tolerance | C1 | Mount tolerance band not defined (WP-O-01 OI-2); calibration limits are wide (pitch -5.2..+9.7 deg, yaw +/-4 deg) | • INS-09 photo instruction (draft) assurance/09-production-operation/WP-O-01-installation-and-provisioning-control.md | 8 | • INS-25 calibration converges; only angles outside the wide limits are rejected assurance/09-production-operation/WP-O-01-installation-and-provisioning-control.md | 8 | H | PFM-ACT-007 · prevention Define the mount position and attitude tolerance band (WP-O-01 OI-2) and check the converged calibration against it | open
PFM-SE-022 I3 Mechanical and electrical installation (INS-09..14) | PFM-FN-007 Mount the device and connect the harness so that the CAN path, relay and camera view are as designed | End Occupant injury in a crash Next higher Cable obstructs or is thrown by the curtain airbag Local Cable crosses the A-pillar or headliner airbag path |  | 10 | PFM-010 · wrong_step Harness routed through an airbag deployment zone | C1 | Routing left to the installer's judgement; airbag zones not marked for the reference vehicle | • INS-12 instruction (draft) assurance/09-production-operation/WP-O-01-installation-and-provisioning-control.md | 7 | • INS-12 routing photo (human review) assurance/09-production-operation/WP-O-01-installation-and-provisioning-control.md | 8 | H | PFM-ACT-005 · prevention Turn WP-O-01 into a recorded checklist (R-DEV, R-INS) with photos and sign-off, and include harness approval list, latch check and airbag-zone routing diagram for the reference vehicle | open
PFM-SE-023 I4 Provisioning: software, firmware, parameters (INS-15..20) | PFM-FN-008 Provision the released software, panda firmware, models and parameter set | End Model-driven longitudinal behaviour or debug control in the vehicle End Contributes to HZ-006 Next higher Unassessed behaviour enabled or attack surface opened Local Parameter set differs from the release record | HZ-005 HZ-006 | 10 | PFM-011 · wrong_parameter Parameters not at the reference values (Experimental Mode on, debug or maneuver modes, SSH) | C1 | Upstream default turns Experimental Mode on (B-06 open); parameters set by hand | • D-08 decided; INS-19 parameter list (draft) assurance/09-production-operation/WP-O-01-installation-and-provisioning-control.md | 8 | • INS-19 parameter dump compared by hand assurance/09-production-operation/WP-O-01-installation-and-provisioning-control.md | 8 | H | PFM-ACT-008 · design change Ship the reference parameter set as release defaults (Chill Mode, B-06; debug modes off; SSH off) and check it at boot | open
PFM-SE-023 I4 Provisioning: software, firmware, parameters (INS-15..20) | PFM-FN-008 Provision the released software, panda firmware, models and parameter set | End Unvalidated lateral and longitudinal behaviour End Contributes to HZ-007 Next higher Unvalidated driving model Local Model files not those of the release | HZ-003 HZ-007 | 10 | PFM-012 · wrong_version Model weights on the device differ from the release | C1 | Model files changed by an update or local edit | • Models pinned by LFS object id in the release tree (D-05) | 3 | • INS-18 hash compare with the release record (manual, script not proven) assurance/09-production-operation/WP-O-01-installation-and-provisioning-control.md | 7 | H | PFM-ACT-006 · detection Write a configuration-check script for INS-18 and INS-21..24 that compares ECU FW versions, model hashes, carParams and pandaStates with the release record and refuses engagement on mismatch (TSR-803) | open
PFM-SE-024 I5 Reference-configuration check (INS-21..24) | PFM-FN-009 Confirm that the item identifies the vehicle as the reference configuration and runs the reference safety mode | End Wrong limits enforced End Contributes to HZ-005 Next higher Wrong controller tuning and, without the lock, wrong envelope Local carParams not those of TOYOTA_COROLLA_TSS2 with parameter 73 | HZ-002 HZ-005 | 10 | PFM-013 · wrong_configuration Item identifies the vehicle wrongly (fuzzy fingerprint or cached CarParams of another car) | C1 | Fuzzy fingerprint accepted at runtime; CarParamsCache can skip the FW query | • Reference lock accepts only TOYOTA with parameter 73 (reference build only, panda#4) panda/board/reference_lock.h | 5 | • INS-22/23 read carParams and pandaStates against the expected values (human check of logs) assurance/09-production-operation/WP-O-01-installation-and-provisioning-control.md | 6 | H | PFM-ACT-006 · detection Write a configuration-check script for INS-18 and INS-21..24 that compares ECU FW versions, model hashes, carParams and pandaStates with the release record and refuses engagement on mismatch (TSR-803) | open
PFM-SE-025 I6 Calibration, functional check and driver briefing (INS-25..30) | PFM-FN-010 Calibrate, prove the stock PCS path and engagement transitions, and brief the driver | End Stock AEB unavailable while the owner relies on it Next higher Relay or forwarding fault undetected Local INS-27 skipped or done without log review | HZ-011 | 10 | PFM-014 · step_omitted Stock PCS path not verified after installation | C1 | Log review of forwarded and intercepted messages is manual and needs tools the installer may not have | • INS-27 instruction (draft) assurance/09-production-operation/WP-O-01-installation-and-provisioning-control.md | 8 | • relayMalfunction alert covers only the relay-not-intercepting case opendbc_repo/opendbc/safety/safety.h | 9 | H | PFM-ACT-009 · detection Provide a log-analysis tool for INS-27 that proves forwarding of stock PCS messages and blocking of intercepted ones | open
PFM-SE-025 I6 Calibration, functional check and driver briefing (INS-25..30) | PFM-FN-010 Calibrate, prove the stock PCS path and engagement transitions, and brief the driver | End Late or no driver intervention End Contributes to HZ-007 Next higher Driver's process model wrong (expects stops at lights, misreads override) Local INS-30 acknowledgement missing | HZ-012 HZ-007 | 10 | PFM-015 · step_omitted Driver not briefed on the item's limits and Chill Mode behaviour | C1 | User information (WP-O-03) not yet written for the reference configuration | • INS-30 instruction (draft) assurance/09-production-operation/WP-O-01-installation-and-provisioning-control.md | 8 | • Signed acknowledgement (human) assurance/09-production-operation/WP-O-01-installation-and-provisioning-control.md | 8 | H | PFM-ACT-010 · prevention Write the user information for the reference configuration (WP-O-03), covering Chill Mode limits and override behaviour | open
PFM-SE-030 U1 Software update and rollback (WP-P-10 §8, WP-O-02) | PFM-FN-011 Update or roll back only to an approved release whose evidence is valid for the installed device | End Unassured configuration driven End Contributes to HZ-005 Next higher Unverified software and possibly panda firmware installed Local Update fetched from an uncontrolled branch | HZ-002 HZ-005 | 10 | PFM-016 · wrong_version Device updates to software that is not an approved LionDriver release | C1 | Updates are git fetches from a configurable branch with no signature check beyond TLS (GAP-26) | • LionDriver controls its release branch (planned) assurance/07-supporting/WP-P-10-release-management.md | 8 | • None at the device; next installation check only | 10 | H | PFM-ACT-011 · design change Signed updates from a LionDriver-controlled branch, and a bench-tested rollback procedure for the device side (GAP-26, WP-S-07, WP-O-02) | open
PFM-SE-030 U1 Software update and rollback (WP-P-10 §8, WP-O-02) | PFM-FN-011 Update or roll back only to an approved release whose evidence is valid for the installed device | End Unverified combination in the vehicle Next higher Envelope behaviour not the one verified with that host Local Host software and panda firmware from different releases | HZ-002 | 10 | PFM-017 · wrong_sequence Rollback to a release whose evidence does not cover the installed panda firmware | C1 | Rollback procedure for the device side not defined yet (WP-O-02) | • WP-P-10 §8 rule: rollback only to a release valid for the installed device assurance/07-supporting/WP-P-10-release-management.md | 7 | • pandad reflashes panda firmware that does not match the host tree openpilot/selfdrive/pandad/pandad.py | 7 | H | PFM-ACT-011 · design change Signed updates from a LionDriver-controlled branch, and a bench-tested rollback procedure for the device side (GAP-26, WP-S-07, WP-O-02) | open

## Actions
Action | Kind | Description | Owner | Status | Causes | Revised S/O/D | Revised AP | Evidence
PFM-ACT-001 | design change | Make RELEASE=1 LIONDRIVER_REFERENCE=1 with the LionDriver key the only release build, and add an automated release check (version contains RELEASE, ALLOW_DEBUG absent, reference lock present) that blocks publication (WP-P-10 §6; SW FMEA SWF-ACT-009) | Jherrod Thomas | open | PFM-001.C1
PFM-ACT-002 | design change | Generate the LionDriver release key offline and define the signing procedure (D-09); remove the debug key from release builds | Jherrod Thomas | open | PFM-002.C1
PFM-ACT-003 | detection | Build the HIL bench (D-04) and define the evidence package location and contents (WP-P-10 §5, OI-2) before the first vehicle-test baseline | Jherrod Thomas | open | PFM-003.C1 PFM-004.C1
PFM-ACT-004 | design change | Set up the LionDriver release channel and an installer that installs only signed release tags and records the installed commit (INS-15) | Jherrod Thomas | open | PFM-005.C1
PFM-ACT-005 | prevention | Turn WP-O-01 into a recorded checklist (R-DEV, R-INS) with photos and sign-off, and include harness approval list, latch check and airbag-zone routing diagram for the reference vehicle | Jherrod Thomas | open | PFM-006.C1 PFM-008.C1 PFM-010.C1
PFM-ACT-006 | detection | Write a configuration-check script for INS-18 and INS-21..24 that compares ECU FW versions, model hashes, carParams and pandaStates with the release record and refuses engagement on mismatch (TSR-803) | Jherrod Thomas | open | PFM-007.C1 PFM-012.C1 PFM-013.C1
PFM-ACT-007 | prevention | Define the mount position and attitude tolerance band (WP-O-01 OI-2) and check the converged calibration against it | Jherrod Thomas | open | PFM-009.C1
PFM-ACT-008 | design change | Ship the reference parameter set as release defaults (Chill Mode, B-06; debug modes off; SSH off) and check it at boot | Jherrod Thomas | open | PFM-011.C1
PFM-ACT-009 | detection | Provide a log-analysis tool for INS-27 that proves forwarding of stock PCS messages and blocking of intercepted ones | Jherrod Thomas | open | PFM-014.C1
PFM-ACT-010 | prevention | Write the user information for the reference configuration (WP-O-03), covering Chill Mode limits and override behaviour | Jherrod Thomas | open | PFM-015.C1
PFM-ACT-011 | design change | Signed updates from a LionDriver-controlled branch, and a bench-tested rollback procedure for the device side (GAP-26, WP-S-07, WP-O-02) | Jherrod Thomas | open | PFM-016.C1 PFM-017.C1

## Structure
Element | Name | Kind | Parent | Functions
PFM-SE-001 | Producing the as-driven reference configuration (AC-001) | process_item
PFM-SE-010 | R1 Freeze and pin the baseline (WP-P-10 §4 steps 1-3) | process_step | PFM-SE-001 | PFM-FN-001: Freeze every component of the release at an identified, protected version
PFM-SE-011 | R2 Build the release (host tree, panda RELEASE firmware; WP-P-10 §4 step 4, §6) | process_step | PFM-SE-001 | PFM-FN-002: Produce the release artifacts, including a panda RELEASE build with the LionDriver key and the reference lock
PFM-SE-012 | R3 Verify and assemble the evidence package (WP-P-10 §4 steps 5-8, §5) | process_step | PFM-SE-001 | PFM-FN-003: Run and archive all required verification on the exact release commit
PFM-SE-013 | R4 Release decision and publication (WP-P-10 §4 steps 9-10) | process_step | PFM-SE-001 | PFM-FN-004: Publish only the approved release through the LionDriver channel
PFM-SE-020 | I1 Incoming inspection (WP-O-01 INS-01..04) | process_step | PFM-SE-001 | PFM-FN-005: Use only the approved, undamaged device and harness
PFM-SE-021 | I2 Vehicle preconditions (INS-05..08) | process_step | PFM-SE-001 | PFM-FN-006: Install only on a vehicle that is in the reference configuration and healthy
PFM-SE-022 | I3 Mechanical and electrical installation (INS-09..14) | process_step | PFM-SE-001 | PFM-FN-007: Mount the device and connect the harness so that the CAN path, relay and camera view are as designed
PFM-SE-023 | I4 Provisioning: software, firmware, parameters (INS-15..20) | process_step | PFM-SE-001 | PFM-FN-008: Provision the released software, panda firmware, models and parameter set
PFM-SE-024 | I5 Reference-configuration check (INS-21..24) | process_step | PFM-SE-001 | PFM-FN-009: Confirm that the item identifies the vehicle as the reference configuration and runs the reference safety mode
PFM-SE-025 | I6 Calibration, functional check and driver briefing (INS-25..30) | process_step | PFM-SE-001 | PFM-FN-010: Calibrate, prove the stock PCS path and engagement transitions, and brief the driver
PFM-SE-030 | U1 Software update and rollback (WP-P-10 §8, WP-O-02) | process_step | PFM-SE-001 | PFM-FN-011: Update or roll back only to an approved release whose evidence is valid for the installed device